## Summary
Metric | Value
Planning Start Date | 2025-06-25
Min Early Delivery Days | 7
Total Orders | 10
Valid Assignments | 10
Invalid Assignments (Past) | 0
Too Early Assignments | 0
Orders On Time | 0
Orders Early (Within Window) | 10
Orders Late | 0
On-Time Percentage (%) | 0.0
Total Penalty Cost ($) | 0.00

## Order_Results
Order Number | Product Id | Customer Priority | Original Promise Date | Optimized Scheduled Date | Delay Days | Is Late | Is Early | Is Too Early | Is Invalid | Order Qty | Revenue
1 | FG2 | Low | 2025-07-07 | 2025-07-06 | -1 | FALSE | TRUE | FALSE | FALSE | 2 | 20000
2 | FG3 | Medium | 2025-07-07 | 2025-07-06 | -1 | FALSE | TRUE | FALSE | FALSE | 4 | 48000
3 | FG4 | High | 2025-07-10 | 2025-07-06 | -4 | FALSE | TRUE | FALSE | FALSE | 1 | 15000
4 | FG2 | High | 2025-08-14 | 2025-08-10 | -4 | FALSE | TRUE | FALSE | FALSE | 2 | 20000
5 | FG3 | Medium | 2025-07-03 | 2025-06-29 | -4 | FALSE | TRUE | FALSE | FALSE | 4 | 48000
6 | FG1 | High | 2025-07-03 | 2025-06-29 | -4 | FALSE | TRUE | FALSE | FALSE | 3 | 15000
7 | FG1 | Medium | 2025-07-07 | 2025-07-06 | -1 | FALSE | TRUE | FALSE | FALSE | 4 | 20000
8 | FG5 | High | 2025-08-07 | 2025-08-03 | -4 | FALSE | TRUE | FALSE | FALSE | 4 | 80000
9 | FG4 | Medium | 2025-08-14 | 2025-08-10 | -4 | FALSE | TRUE | FALSE | FALSE | 4 | 60000
10 | FG5 | Medium | 2025-07-15 | 2025-07-13 | -2 | FALSE | TRUE | FALSE | FALSE | 2 | 40000

## Priority_Analysis
Customer Priority | Total Orders | Late Orders | On Time Rate | Avg Delay Days | Total Revenue
Low | 1 | 0 | 100.0 | 0.0 | 20000.00
Medium | 5 | 0 | 100.0 | 0.0 | 216000.00
High | 4 | 0 | 100.0 | 0.0 | 130000.00

## Capacity_Utilization
Line Restriction | Max Weekly Usage | Total Usage | Average Usage | Peak Utilization
Welding_LineB | 10 | 21 | 7.0 | 0
Assembly_C | 8 | 20 | 5.0 | 0
Welding_LineA | 14 | 25 | 6.3 | 0
Testing_Station | 6 | 10 | 5.0 | 0
Assembly_D | 8 | 18 | 4.5 | 0
Paint_Line | 10 | 26 | 8.7 | 0

## Capacity_Pivot_Table
Line Restriction | Week | Scheduled Quantity
Welding_LineB | W2025-27 | 10
Welding_LineB | W2025-26 | 7
Welding_LineB | W2025-32 | 4
Assembly_C | W2025-27 | 4
Assembly_C | W2025-26 | 4
Assembly_C | W2025-32 | 4
Assembly_C | W2025-28 | 8
Welding_LineA | W2025-27 | 14
Welding_LineA | W2025-26 | 3
Welding_LineA | W2025-31 | 4
Welding_LineA | W2025-32 | 4
Testing_Station | W2025-27 | 6
Testing_Station | W2025-32 | 4
Assembly_D | W2025-27 | 2
Assembly_D | W2025-32 | 8
Assembly_D | W2025-26 | 4
Assembly_D | W2025-31 | 4
Paint_Line | W2025-26 | 10
Paint_Line | W2025-27 | 8
Paint_Line | W2025-31 | 8

## Weekly_Schedule
Order Number | Product Id | Scheduled Date | Operation Id | Line Restriction | Quantity | Customer Priority
1 | FG2 | 2025-07-06 | 100 | Welding_LineB | 2 | Low
1 | FG2 | 2025-07-06 | 200 | Assembly_C | 2 | Low
1 | FG2 | 2025-07-06 | 300 | Assembly_C | 2 | Low
1 | FG2 | 2025-07-06 | 400 | Welding_LineA | 2 | Low
2 | FG3 | 2025-07-06 | 100 | Welding_LineB | 4 | Medium
2 | FG3 | 2025-07-06 | 200 | Welding_LineA | 4 | Medium
2 | FG3 | 2025-07-06 | 300 | Welding_LineB | 4 | Medium
2 | FG3 | 2025-07-06 | 400 | Testing_Station | 4 | Medium
3 | FG4 | 2025-07-06 | 100 | Assembly_D | 1 | High
3 | FG4 | 2025-07-06 | 200 | Testing_Station | 1 | High
3 | FG4 | 2025-07-06 | 300 | Testing_Station | 1 | High
3 | FG4 | 2025-07-06 | 400 | Assembly_D | 1 | High
4 | FG2 | 2025-08-10 | 100 | Assembly_D | 2 | High
4 | FG2 | 2025-08-10 | 200 | Assembly_D | 2 | High
4 | FG2 | 2025-08-10 | 300 | Assembly_D | 2 | High
4 | FG2 | 2025-08-10 | 400 | Assembly_D | 2 | High
5 | FG3 | 2025-06-29 | 100 | Welding_LineB | 4 | Medium
5 | FG3 | 2025-06-29 | 200 | Assembly_D | 4 | Medium
5 | FG3 | 2025-06-29 | 300 | Assembly_C | 4 | Medium
5 | FG3 | 2025-06-29 | 400 | Paint_Line | 4 | Medium
6 | FG1 | 2025-06-29 | 100 | Paint_Line | 3 | High
6 | FG1 | 2025-06-29 | 200 | Welding_LineA | 3 | High
6 | FG1 | 2025-06-29 | 300 | Paint_Line | 3 | High
6 | FG1 | 2025-06-29 | 400 | Welding_LineB | 3 | High
7 | FG1 | 2025-07-06 | 100 | Paint_Line | 4 | Medium
7 | FG1 | 2025-07-06 | 200 | Paint_Line | 4 | Medium
7 | FG1 | 2025-07-06 | 300 | Welding_LineA | 4 | Medium
7 | FG1 | 2025-07-06 | 400 | Welding_LineA | 4 | Medium
8 | FG5 | 2025-08-03 | 100 | Paint_Line | 4 | High
8 | FG5 | 2025-08-03 | 200 | Assembly_D | 4 | High
8 | FG5 | 2025-08-03 | 300 | Welding_LineA | 4 | High
8 | FG5 | 2025-08-03 | 400 | Paint_Line | 4 | High
9 | FG4 | 2025-08-10 | 100 | Welding_LineB | 4 | Medium
9 | FG4 | 2025-08-10 | 200 | Welding_LineA | 4 | Medium
9 | FG4 | 2025-08-10 | 300 | Testing_Station | 4 | Medium
9 | FG4 | 2025-08-10 | 400 | Assembly_C | 4 | Medium
10 | FG5 | 2025-07-13 | 100 | Assembly_C | 2 | Medium
10 | FG5 | 2025-07-13 | 200 | Assembly_C | 2 | Medium
10 | FG5 | 2025-07-13 | 300 | Assembly_C | 2 | Medium
10 | FG5 | 2025-07-13 | 400 | Assembly_C | 2 | Medium

## Fitness_Evolution
Generation | Fitness Score
1 | 88137.9706
2 | 99842
3 | 99842
4 | 99842
5 | 99842
6 | 99842
7 | 99842
8 | 99842
9 | 99842
10 | 99842
11 | 99842
12 | 99842
13 | 99842
14 | 99842
15 | 99842
16 | 99842
17 | 99842
18 | 99842
19 | 99842
20 | 100142
21 | 100142
22 | 100271
23 | 100271
24 | 100271
25 | 100271
26 | 100271
27 | 100271
28 | 100271
29 | 100271
30 | 100271
31 | 100271
32 | 100271
33 | 100271
34 | 100271
35 | 100271
36 | 100271
37 | 100271
38 | 100271
39 | 100271
40 | 100271
41 | 100271
42 | 100271
43 | 100271
44 | 100271
45 | 100271
46 | 100271
47 | 100271
48 | 100271
49 | 100271
50 | 100271
51 | 100271
52 | 100271
53 | 100271
54 | 100271
55 | 100271
56 | 100271
57 | 100271
58 | 100271
59 | 100271
60 | 100271
61 | 100271
62 | 100271
63 | 100271
64 | 100271
65 | 100271
66 | 100271
67 | 100271
68 | 100271
69 | 100271
70 | 100271
71 | 100271
72 | 100271
73 | 100271
74 | 100271
75 | 100271
76 | 100271
77 | 100271
78 | 100271
79 | 100271
80 | 100271
81 | 100271
82 | 100271
83 | 100271
84 | 100271
85 | 100271
86 | 100271
87 | 100271
88 | 100271
89 | 100271
90 | 100271
91 | 100271
92 | 100271
93 | 100271
94 | 100271
95 | 100271
96 | 100271
97 | 100271
98 | 100271
99 | 100271
100 | 100271

## Component_Analysis
Component | Max Weekly Usage | Total Usage | Peak Utilization
Engine | 11 | 30 | 0
Chassis | 11 | 30 | 0
Hydraulics | 14 | 42 | 0
Electronics | 11 | 30 | 0
Tires | 44 | 120 | 0
Battery | 8 | 18 | 0