## Summary
Metric | Value
Planning Start Date | 2025-06-19
Min Early Delivery Days | 7
Total Orders | 50
Valid Assignments | 43
Invalid Assignments (Past) | 0
Too Early Assignments | 0
Orders On Time | 0
Orders Early (Within Window) | 4
Orders Late | 39
On-Time Percentage (%) | 0.0
Total Penalty Cost ($) | 11625.00

## Order_Results
Order Number | Product Id | Customer Priority | Original Promise Date | Optimized Scheduled Date | Delay Days | Is Late | Is Early | Is Too Early | Is Invalid | Order Qty | Revenue
SO0001 | FL004 | Low | 2025-07-10 | 2025-07-27 | 16 | TRUE | FALSE | FALSE | FALSE | 5 | 106367.4146
SO0002 | FL004 | High | 2025-07-10 | 2025-09-07 | 58 | TRUE | FALSE | FALSE | FALSE | 5 | 105396.8465
SO0003 | FL004 | Low | 2025-07-03 | 2025-08-10 | 37 | TRUE | FALSE | FALSE | FALSE | 5 | 213338.1386
SO0004 | FL002 | Medium | 2025-07-24 | 2025-08-31 | 37 | TRUE | FALSE | FALSE | FALSE | 4 | 130377.75
SO0005 | FL001 | Medium | 2025-07-31 | 2025-07-27 | -4 | FALSE | TRUE | FALSE | FALSE | 2 | 39668.8301
SO0006 | FL002 | Low | 2025-07-03 | 2025-06-22 | -11 | FALSE | FALSE | TRUE | FALSE | 2 | 77302.1239
SO0007 | FL004 | High | 2025-08-21 | 2025-08-31 | 9 | TRUE | FALSE | FALSE | FALSE | 1 | 31943.6447
SO0008 | FL003 | Medium | 2025-07-10 | 2025-07-20 | 9 | TRUE | FALSE | FALSE | FALSE | 2 | 37714.2494
SO0009 | FL005 | Low | 2025-08-28 | 2025-10-05 | 37 | TRUE | FALSE | FALSE | FALSE | 5 | 105864.6333
SO0010 | FL001 | High | 2025-07-31 | 2025-07-27 | -4 | FALSE | TRUE | FALSE | FALSE | 1 | 41630.5147
SO0011 | FL003 | Low | 2025-08-28 | 2025-10-19 | 51 | TRUE | FALSE | FALSE | FALSE | 3 | 102295.0679
SO0012 | FL002 | High | 2025-07-24 | 2025-08-24 | 30 | TRUE | FALSE | FALSE | FALSE | 2 | 39924.8124
SO0013 | FL004 | Medium | 2025-07-10 | 2025-09-28 | 79 | TRUE | FALSE | FALSE | FALSE | 1 | 37435.8675
SO0014 | FL003 | High | 2025-07-10 | 2025-07-13 | 2 | TRUE | FALSE | FALSE | FALSE | 3 | 47961.4619
SO0015 | FL001 | High | 2025-08-28 | 2025-08-17 | -11 | FALSE | FALSE | TRUE | FALSE | 5 | 121520.1416
SO0016 | FL003 | High | 2025-07-10 | 2025-08-10 | 30 | TRUE | FALSE | FALSE | FALSE | 1 | 32717.4471
SO0017 | FL002 | Low | 2025-06-26 | 2025-07-27 | 30 | TRUE | FALSE | FALSE | FALSE | 2 | 98243.0483
SO0018 | FL001 | Medium | 2025-07-10 | 2025-10-12 | 93 | TRUE | FALSE | FALSE | FALSE | 4 | 183226.2432
SO0019 | FL002 | Medium | 2025-09-04 | 2025-09-14 | 9 | TRUE | FALSE | FALSE | FALSE | 4 | 89379.4185
SO0020 | FL002 | Medium | 2025-08-07 | 2025-08-31 | 23 | TRUE | FALSE | FALSE | FALSE | 4 | 114583.8624
SO0021 | FL001 | High | 2025-08-28 | 2025-09-28 | 30 | TRUE | FALSE | FALSE | FALSE | 2 | 80206.9653
SO0022 | FL003 | Low | 2025-07-17 | 2025-10-05 | 79 | TRUE | FALSE | FALSE | FALSE | 2 | 47062.9514
SO0023 | FL005 | Low | 2025-08-21 | 2025-08-10 | -11 | FALSE | FALSE | TRUE | FALSE | 2 | 70824.5529
SO0024 | FL002 | High | 2025-07-10 | 2025-07-20 | 9 | TRUE | FALSE | FALSE | FALSE | 3 | 102779.2572
SO0025 | FL004 | Low | 2025-06-26 | 2025-06-22 | -4 | FALSE | TRUE | FALSE | FALSE | 2 | 58251.1002
SO0026 | FL005 | Medium | 2025-08-07 | 2025-08-24 | 16 | TRUE | FALSE | FALSE | FALSE | 2 | 59711.0575
SO0027 | FL004 | High | 2025-07-10 | 2025-11-02 | 114 | TRUE | FALSE | FALSE | FALSE | 5 | 238768.8522
SO0028 | FL003 | Low | 2025-07-03 | 2025-07-06 | 2 | TRUE | FALSE | FALSE | FALSE | 2 | 60478.5362
SO0029 | FL005 | Low | 2025-08-21 | 2025-10-12 | 51 | TRUE | FALSE | FALSE | FALSE | 1 | 24562.827
SO0030 | FL005 | Low | 2025-07-24 | 2025-08-17 | 23 | TRUE | FALSE | FALSE | FALSE | 5 | 234291.6234
SO0031 | FL001 | Medium | 2025-07-31 | 2025-09-28 | 58 | TRUE | FALSE | FALSE | FALSE | 4 | 176831.2307
SO0032 | FL002 | High | 2025-08-14 | 2025-08-03 | -11 | FALSE | FALSE | TRUE | FALSE | 2 | 62629.7848
SO0033 | FL004 | Medium | 2025-08-07 | 2025-08-17 | 9 | TRUE | FALSE | FALSE | FALSE | 1 | 26170.8574
SO0034 | FL001 | High | 2025-08-28 | 2025-09-21 | 23 | TRUE | FALSE | FALSE | FALSE | 2 | 88814.1169
SO0035 | FL004 | Medium | 2025-08-21 | 2025-08-17 | -4 | FALSE | TRUE | FALSE | FALSE | 4 | 150323.1405
SO0036 | FL005 | Low | 2025-07-03 | 2025-07-27 | 23 | TRUE | FALSE | FALSE | FALSE | 5 | 203931.0907
SO0037 | FL002 | High | 2025-07-03 | 2025-07-20 | 16 | TRUE | FALSE | FALSE | FALSE | 3 | 105324.9716
SO0038 | FL005 | Low | 2025-07-03 | 2025-07-27 | 23 | TRUE | FALSE | FALSE | FALSE | 1 | 41342.6546
SO0039 | FL001 | High | 2025-06-26 | 2025-06-29 | 2 | TRUE | FALSE | FALSE | FALSE | 3 | 46198.2563
SO0040 | FL003 | Medium | 2025-07-24 | 2025-11-02 | 100 | TRUE | FALSE | FALSE | FALSE | 5 | 90665.7563
SO0041 | FL005 | Low | 2025-09-04 | 2025-09-21 | 16 | TRUE | FALSE | FALSE | FALSE | 4 | 80473.9864
SO0042 | FL001 | Low | 2025-09-11 | 2025-09-28 | 16 | TRUE | FALSE | FALSE | FALSE | 1 | 26197.6056
SO0043 | FL005 | Low | 2025-09-04 | 2025-10-19 | 44 | TRUE | FALSE | FALSE | FALSE | 4 | 73268.2337
SO0044 | FL005 | Low | 2025-09-04 | 2025-10-12 | 37 | TRUE | FALSE | FALSE | FALSE | 1 | 23723.9088
SO0045 | FL004 | Low | 2025-07-10 | 2025-06-29 | -11 | FALSE | FALSE | TRUE | FALSE | 3 | 140656.0495
SO0046 | FL004 | Low | 2025-08-28 | 2025-10-12 | 44 | TRUE | FALSE | FALSE | FALSE | 2 | 32909.337
SO0047 | FL002 | Medium | 2025-08-07 | 2025-07-27 | -11 | FALSE | FALSE | TRUE | FALSE | 2 | 82565.0481
SO0048 | FL004 | Medium | 2025-07-10 | 2025-07-20 | 9 | TRUE | FALSE | FALSE | FALSE | 3 | 127569.1229
SO0049 | FL005 | High | 2025-08-14 | 2025-08-03 | -11 | FALSE | FALSE | TRUE | FALSE | 3 | 58237.2546
SO0050 | FL003 | High | 2025-08-28 | 2025-09-28 | 30 | TRUE | FALSE | FALSE | FALSE | 3 | 93544.8757

## Priority_Analysis
Customer Priority | Total Orders | Late Orders | On Time Rate | Avg Delay Days | Total Revenue
Low | 20 | 16 | 20.0 | 33.1 | 1821384.88
High | 16 | 12 | 25.0 | 29.4 | 1297599.20
Medium | 14 | 11 | 21.4 | 40.2 | 1346222.43

## Capacity_Utilization
Line Restriction | Max Weekly Usage | Total Usage | Peak Utilization
Welding_Line2 | 15 | 63 | 0
Assembly_B | 10 | 78 | 0
Paint_Line | 18 | 143 | 0
Testing_Station | 18 | 143 | 0
Welding_Line1 | 7 | 80 | 0
Assembly_A | 10 | 65 | 0

## Weekly_Schedule
Order Number | Product Id | Scheduled Date | Operation Id | Line Restriction | Quantity | Customer Priority
SO0001 | FL004 | 2025-07-27 | 0010 | Welding_Line2 | 5 | Low
SO0001 | FL004 | 2025-07-27 | 0020 | Assembly_B | 5 | Low
SO0001 | FL004 | 2025-07-27 | 0030 | Paint_Line | 5 | Low
SO0001 | FL004 | 2025-07-27 | 0040 | Testing_Station | 5 | Low
SO0002 | FL004 | 2025-09-07 | 0010 | Welding_Line1 | 5 | High
SO0002 | FL004 | 2025-09-07 | 0020 | Assembly_A | 5 | High
SO0002 | FL004 | 2025-09-07 | 0030 | Paint_Line | 5 | High
SO0002 | FL004 | 2025-09-07 | 0040 | Testing_Station | 5 | High
SO0003 | FL004 | 2025-08-10 | 0010 | Welding_Line1 | 5 | Low
SO0003 | FL004 | 2025-08-10 | 0020 | Assembly_B | 5 | Low
SO0003 | FL004 | 2025-08-10 | 0030 | Paint_Line | 5 | Low
SO0003 | FL004 | 2025-08-10 | 0040 | Testing_Station | 5 | Low
SO0004 | FL002 | 2025-08-31 | 0010 | Welding_Line2 | 4 | Medium
SO0004 | FL002 | 2025-08-31 | 0020 | Assembly_A | 4 | Medium
SO0004 | FL002 | 2025-08-31 | 0030 | Paint_Line | 4 | Medium
SO0004 | FL002 | 2025-08-31 | 0040 | Testing_Station | 4 | Medium
SO0005 | FL001 | 2025-07-27 | 0010 | Welding_Line1 | 2 | Medium
SO0005 | FL001 | 2025-07-27 | 0020 | Assembly_A | 2 | Medium
SO0005 | FL001 | 2025-07-27 | 0030 | Paint_Line | 2 | Medium
SO0005 | FL001 | 2025-07-27 | 0040 | Testing_Station | 2 | Medium
SO0006 | FL002 | 2025-06-22 | 0010 | Welding_Line1 | 2 | Low
SO0006 | FL002 | 2025-06-22 | 0020 | Assembly_B | 2 | Low
SO0006 | FL002 | 2025-06-22 | 0030 | Paint_Line | 2 | Low
SO0006 | FL002 | 2025-06-22 | 0040 | Testing_Station | 2 | Low
SO0007 | FL004 | 2025-08-31 | 0010 | Welding_Line1 | 1 | High
SO0007 | FL004 | 2025-08-31 | 0020 | Assembly_A | 1 | High
SO0007 | FL004 | 2025-08-31 | 0030 | Paint_Line | 1 | High
SO0007 | FL004 | 2025-08-31 | 0040 | Testing_Station | 1 | High
SO0008 | FL003 | 2025-07-20 | 0010 | Welding_Line1 | 2 | Medium
SO0008 | FL003 | 2025-07-20 | 0020 | Assembly_A | 2 | Medium
SO0008 | FL003 | 2025-07-20 | 0030 | Paint_Line | 2 | Medium
SO0008 | FL003 | 2025-07-20 | 0040 | Testing_Station | 2 | Medium
SO0009 | FL005 | 2025-10-05 | 0010 | Welding_Line1 | 5 | Low
SO0009 | FL005 | 2025-10-05 | 0020 | Assembly_B | 5 | Low
SO0009 | FL005 | 2025-10-05 | 0030 | Paint_Line | 5 | Low
SO0009 | FL005 | 2025-10-05 | 0040 | Testing_Station | 5 | Low
SO0010 | FL001 | 2025-07-27 | 0010 | Welding_Line1 | 1 | High
SO0010 | FL001 | 2025-07-27 | 0020 | Assembly_A | 1 | High
SO0010 | FL001 | 2025-07-27 | 0030 | Paint_Line | 1 | High
SO0010 | FL001 | 2025-07-27 | 0040 | Testing_Station | 1 | High
SO0011 | FL003 | 2025-10-19 | 0010 | Welding_Line1 | 3 | Low
SO0011 | FL003 | 2025-10-19 | 0020 | Assembly_B | 3 | Low
SO0011 | FL003 | 2025-10-19 | 0030 | Paint_Line | 3 | Low
SO0011 | FL003 | 2025-10-19 | 0040 | Testing_Station | 3 | Low
SO0012 | FL002 | 2025-08-24 | 0010 | Welding_Line1 | 2 | High
SO0012 | FL002 | 2025-08-24 | 0020 | Assembly_B | 2 | High
SO0012 | FL002 | 2025-08-24 | 0030 | Paint_Line | 2 | High
SO0012 | FL002 | 2025-08-24 | 0040 | Testing_Station | 2 | High
SO0013 | FL004 | 2025-09-28 | 0010 | Welding_Line2 | 1 | Medium
SO0013 | FL004 | 2025-09-28 | 0020 | Assembly_B | 1 | Medium
SO0013 | FL004 | 2025-09-28 | 0030 | Paint_Line | 1 | Medium
SO0013 | FL004 | 2025-09-28 | 0040 | Testing_Station | 1 | Medium
SO0014 | FL003 | 2025-07-13 | 0010 | Welding_Line2 | 3 | High
SO0014 | FL003 | 2025-07-13 | 0020 | Assembly_B | 3 | High
SO0014 | FL003 | 2025-07-13 | 0030 | Paint_Line | 3 | High
SO0014 | FL003 | 2025-07-13 | 0040 | Testing_Station | 3 | High
SO0015 | FL001 | 2025-08-17 | 0010 | Welding_Line2 | 5 | High
SO0015 | FL001 | 2025-08-17 | 0020 | Assembly_A | 5 | High
SO0015 | FL001 | 2025-08-17 | 0030 | Paint_Line | 5 | High
SO0015 | FL001 | 2025-08-17 | 0040 | Testing_Station | 5 | High
SO0016 | FL003 | 2025-08-10 | 0010 | Welding_Line2 | 1 | High
SO0016 | FL003 | 2025-08-10 | 0020 | Assembly_A | 1 | High
SO0016 | FL003 | 2025-08-10 | 0030 | Paint_Line | 1 | High
SO0016 | FL003 | 2025-08-10 | 0040 | Testing_Station | 1 | High
SO0017 | FL002 | 2025-07-27 | 0010 | Welding_Line2 | 2 | Low
SO0017 | FL002 | 2025-07-27 | 0020 | Assembly_A | 2 | Low
SO0017 | FL002 | 2025-07-27 | 0030 | Paint_Line | 2 | Low
SO0017 | FL002 | 2025-07-27 | 0040 | Testing_Station | 2 | Low
SO0018 | FL001 | 2025-10-12 | 0010 | Welding_Line1 | 4 | Medium
SO0018 | FL001 | 2025-10-12 | 0020 | Assembly_B | 4 | Medium
SO0018 | FL001 | 2025-10-12 | 0030 | Paint_Line | 4 | Medium
SO0018 | FL001 | 2025-10-12 | 0040 | Testing_Station | 4 | Medium
SO0019 | FL002 | 2025-09-14 | 0010 | Welding_Line1 | 4 | Medium
SO0019 | FL002 | 2025-09-14 | 0020 | Assembly_A | 4 | Medium
SO0019 | FL002 | 2025-09-14 | 0030 | Paint_Line | 4 | Medium
SO0019 | FL002 | 2025-09-14 | 0040 | Testing_Station | 4 | Medium
SO0020 | FL002 | 2025-08-31 | 0010 | Welding_Line1 | 4 | Medium
SO0020 | FL002 | 2025-08-31 | 0020 | Assembly_A | 4 | Medium
SO0020 | FL002 | 2025-08-31 | 0030 | Paint_Line | 4 | Medium
SO0020 | FL002 | 2025-08-31 | 0040 | Testing_Station | 4 | Medium
SO0021 | FL001 | 2025-09-28 | 0010 | Welding_Line2 | 2 | High
SO0021 | FL001 | 2025-09-28 | 0020 | Assembly_B | 2 | High
SO0021 | FL001 | 2025-09-28 | 0030 | Paint_Line | 2 | High
SO0021 | FL001 | 2025-09-28 | 0040 | Testing_Station | 2 | High
SO0022 | FL003 | 2025-10-05 | 0010 | Welding_Line2 | 2 | Low
SO0022 | FL003 | 2025-10-05 | 0020 | Assembly_B | 2 | Low
SO0022 | FL003 | 2025-10-05 | 0030 | Paint_Line | 2 | Low
SO0022 | FL003 | 2025-10-05 | 0040 | Testing_Station | 2 | Low
SO0023 | FL005 | 2025-08-10 | 0010 | Welding_Line2 | 2 | Low
SO0023 | FL005 | 2025-08-10 | 0020 | Assembly_A | 2 | Low
SO0023 | FL005 | 2025-08-10 | 0030 | Paint_Line | 2 | Low
SO0023 | FL005 | 2025-08-10 | 0040 | Testing_Station | 2 | Low
SO0024 | FL002 | 2025-07-20 | 0010 | Welding_Line2 | 3 | High
SO0024 | FL002 | 2025-07-20 | 0020 | Assembly_A | 3 | High
SO0024 | FL002 | 2025-07-20 | 0030 | Paint_Line | 3 | High
SO0024 | FL002 | 2025-07-20 | 0040 | Testing_Station | 3 | High
SO0025 | FL004 | 2025-06-22 | 0010 | Welding_Line1 | 2 | Low
SO0025 | FL004 | 2025-06-22 | 0020 | Assembly_B | 2 | Low
SO0025 | FL004 | 2025-06-22 | 0030 | Paint_Line | 2 | Low
SO0025 | FL004 | 2025-06-22 | 0040 | Testing_Station | 2 | Low
SO0026 | FL005 | 2025-08-24 | 0010 | Welding_Line2 | 2 | Medium
SO0026 | FL005 | 2025-08-24 | 0020 | Assembly_B | 2 | Medium
SO0026 | FL005 | 2025-08-24 | 0030 | Paint_Line | 2 | Medium
SO0026 | FL005 | 2025-08-24 | 0040 | Testing_Station | 2 | Medium
SO0027 | FL004 | 2025-11-02 | 0010 | Welding_Line2 | 5 | High
SO0027 | FL004 | 2025-11-02 | 0020 | Assembly_A | 5 | High
SO0027 | FL004 | 2025-11-02 | 0030 | Paint_Line | 5 | High
SO0027 | FL004 | 2025-11-02 | 0040 | Testing_Station | 5 | High
SO0028 | FL003 | 2025-07-06 | 0010 | Welding_Line1 | 2 | Low
SO0028 | FL003 | 2025-07-06 | 0020 | Assembly_B | 2 | Low
SO0028 | FL003 | 2025-07-06 | 0030 | Paint_Line | 2 | Low
SO0028 | FL003 | 2025-07-06 | 0040 | Testing_Station | 2 | Low
SO0029 | FL005 | 2025-10-12 | 0010 | Welding_Line1 | 1 | Low
SO0029 | FL005 | 2025-10-12 | 0020 | Assembly_A | 1 | Low
SO0029 | FL005 | 2025-10-12 | 0030 | Paint_Line | 1 | Low
SO0029 | FL005 | 2025-10-12 | 0040 | Testing_Station | 1 | Low
SO0030 | FL005 | 2025-08-17 | 0010 | Welding_Line1 | 5 | Low
SO0030 | FL005 | 2025-08-17 | 0020 | Assembly_A | 5 | Low
SO0030 | FL005 | 2025-08-17 | 0030 | Paint_Line | 5 | Low
SO0030 | FL005 | 2025-08-17 | 0040 | Testing_Station | 5 | Low
SO0031 | FL001 | 2025-09-28 | 0010 | Welding_Line2 | 4 | Medium
SO0031 | FL001 | 2025-09-28 | 0020 | Assembly_B | 4 | Medium
SO0031 | FL001 | 2025-09-28 | 0030 | Paint_Line | 4 | Medium
SO0031 | FL001 | 2025-09-28 | 0040 | Testing_Station | 4 | Medium
SO0032 | FL002 | 2025-08-03 | 0010 | Welding_Line2 | 2 | High
SO0032 | FL002 | 2025-08-03 | 0020 | Assembly_B | 2 | High
SO0032 | FL002 | 2025-08-03 | 0030 | Paint_Line | 2 | High
SO0032 | FL002 | 2025-08-03 | 0040 | Testing_Station | 2 | High
SO0033 | FL004 | 2025-08-17 | 0010 | Welding_Line1 | 1 | Medium
SO0033 | FL004 | 2025-08-17 | 0020 | Assembly_B | 1 | Medium
SO0033 | FL004 | 2025-08-17 | 0030 | Paint_Line | 1 | Medium
SO0033 | FL004 | 2025-08-17 | 0040 | Testing_Station | 1 | Medium
SO0034 | FL001 | 2025-09-21 | 0010 | Welding_Line1 | 2 | High
SO0034 | FL001 | 2025-09-21 | 0020 | Assembly_A | 2 | High
SO0034 | FL001 | 2025-09-21 | 0030 | Paint_Line | 2 | High
SO0034 | FL001 | 2025-09-21 | 0040 | Testing_Station | 2 | High
SO0035 | FL004 | 2025-08-17 | 0010 | Welding_Line2 | 4 | Medium
SO0035 | FL004 | 2025-08-17 | 0020 | Assembly_B | 4 | Medium
SO0035 | FL004 | 2025-08-17 | 0030 | Paint_Line | 4 | Medium
SO0035 | FL004 | 2025-08-17 | 0040 | Testing_Station | 4 | Medium
SO0036 | FL005 | 2025-07-27 | 0010 | Welding_Line2 | 5 | Low
SO0036 | FL005 | 2025-07-27 | 0020 | Assembly_B | 5 | Low
SO0036 | FL005 | 2025-07-27 | 0030 | Paint_Line | 5 | Low
SO0036 | FL005 | 2025-07-27 | 0040 | Testing_Station | 5 | Low
SO0037 | FL002 | 2025-07-20 | 0010 | Welding_Line2 | 3 | High
SO0037 | FL002 | 2025-07-20 | 0020 | Assembly_B | 3 | High
SO0037 | FL002 | 2025-07-20 | 0030 | Paint_Line | 3 | High
SO0037 | FL002 | 2025-07-20 | 0040 | Testing_Station | 3 | High
SO0038 | FL005 | 2025-07-27 | 0010 | Welding_Line2 | 1 | Low
SO0038 | FL005 | 2025-07-27 | 0020 | Assembly_A | 1 | Low
SO0038 | FL005 | 2025-07-27 | 0030 | Paint_Line | 1 | Low
SO0038 | FL005 | 2025-07-27 | 0040 | Testing_Station | 1 | Low
SO0039 | FL001 | 2025-06-29 | 0010 | Welding_Line2 | 3 | High
SO0039 | FL001 | 2025-06-29 | 0020 | Assembly_B | 3 | High
SO0039 | FL001 | 2025-06-29 | 0030 | Paint_Line | 3 | High
SO0039 | FL001 | 2025-06-29 | 0040 | Testing_Station | 3 | High
SO0040 | FL003 | 2025-11-02 | 0010 | Welding_Line1 | 5 | Medium
SO0040 | FL003 | 2025-11-02 | 0020 | Assembly_B | 5 | Medium
SO0040 | FL003 | 2025-11-02 | 0030 | Paint_Line | 5 | Medium
SO0040 | FL003 | 2025-11-02 | 0040 | Testing_Station | 5 | Medium
SO0041 | FL005 | 2025-09-21 | 0010 | Welding_Line1 | 4 | Low
SO0041 | FL005 | 2025-09-21 | 0020 | Assembly_A | 4 | Low
SO0041 | FL005 | 2025-09-21 | 0030 | Paint_Line | 4 | Low
SO0041 | FL005 | 2025-09-21 | 0040 | Testing_Station | 4 | Low
SO0042 | FL001 | 2025-09-28 | 0010 | Welding_Line1 | 1 | Low
SO0042 | FL001 | 2025-09-28 | 0020 | Assembly_B | 1 | Low
SO0042 | FL001 | 2025-09-28 | 0030 | Paint_Line | 1 | Low
SO0042 | FL001 | 2025-09-28 | 0040 | Testing_Station | 1 | Low
SO0043 | FL005 | 2025-10-19 | 0010 | Welding_Line1 | 4 | Low
SO0043 | FL005 | 2025-10-19 | 0020 | Assembly_B | 4 | Low
SO0043 | FL005 | 2025-10-19 | 0030 | Paint_Line | 4 | Low
SO0043 | FL005 | 2025-10-19 | 0040 | Testing_Station | 4 | Low
SO0044 | FL005 | 2025-10-12 | 0010 | Welding_Line1 | 1 | Low
SO0044 | FL005 | 2025-10-12 | 0020 | Assembly_A | 1 | Low
SO0044 | FL005 | 2025-10-12 | 0030 | Paint_Line | 1 | Low
SO0044 | FL005 | 2025-10-12 | 0040 | Testing_Station | 1 | Low
SO0045 | FL004 | 2025-06-29 | 0010 | Welding_Line1 | 3 | Low
SO0045 | FL004 | 2025-06-29 | 0020 | Assembly_B | 3 | Low
SO0045 | FL004 | 2025-06-29 | 0030 | Paint_Line | 3 | Low
SO0045 | FL004 | 2025-06-29 | 0040 | Testing_Station | 3 | Low
SO0046 | FL004 | 2025-10-12 | 0010 | Welding_Line2 | 2 | Low
SO0046 | FL004 | 2025-10-12 | 0020 | Assembly_A | 2 | Low
SO0046 | FL004 | 2025-10-12 | 0030 | Paint_Line | 2 | Low
SO0046 | FL004 | 2025-10-12 | 0040 | Testing_Station | 2 | Low
SO0047 | FL002 | 2025-07-27 | 0010 | Welding_Line2 | 2 | Medium
SO0047 | FL002 | 2025-07-27 | 0020 | Assembly_A | 2 | Medium
SO0047 | FL002 | 2025-07-27 | 0030 | Paint_Line | 2 | Medium
SO0047 | FL002 | 2025-07-27 | 0040 | Testing_Station | 2 | Medium
SO0048 | FL004 | 2025-07-20 | 0010 | Welding_Line1 | 3 | Medium
SO0048 | FL004 | 2025-07-20 | 0020 | Assembly_A | 3 | Medium
SO0048 | FL004 | 2025-07-20 | 0030 | Paint_Line | 3 | Medium
SO0048 | FL004 | 2025-07-20 | 0040 | Testing_Station | 3 | Medium
SO0049 | FL005 | 2025-08-03 | 0010 | Welding_Line1 | 3 | High
SO0049 | FL005 | 2025-08-03 | 0020 | Assembly_B | 3 | High
SO0049 | FL005 | 2025-08-03 | 0030 | Paint_Line | 3 | High
SO0049 | FL005 | 2025-08-03 | 0040 | Testing_Station | 3 | High
SO0050 | FL003 | 2025-09-28 | 0010 | Welding_Line1 | 3 | High
SO0050 | FL003 | 2025-09-28 | 0020 | Assembly_A | 3 | High
SO0050 | FL003 | 2025-09-28 | 0030 | Paint_Line | 3 | High
SO0050 | FL003 | 2025-09-28 | 0040 | Testing_Station | 3 | High

## Fitness_Evolution
Generation | Fitness Score
1 | 73450
2 | 79175
3 | 82355
4 | 83780
5 | 83780
6 | 83780
7 | 83780
8 | 83780
9 | 83780
10 | 83780
11 | 83780
12 | 83780
13 | 83780
14 | 83780
15 | 83780
16 | 83780
17 | 83780
18 | 84590
19 | 84590
20 | 84590
21 | 84590
22 | 84590
23 | 84705
24 | 85365
25 | 85365
26 | 85365
27 | 85365
28 | 85365
29 | 85365
30 | 85365
31 | 85365
32 | 85365
33 | 85365
34 | 85365
35 | 85365
36 | 85365
37 | 85365
38 | 85365
39 | 85365
40 | 85365
41 | 85365
42 | 85365
43 | 86005
44 | 86005
45 | 86005
46 | 86005
47 | 86005
48 | 86005
49 | 86005
50 | 86005
51 | 86005
52 | 86005
53 | 86005
54 | 86005
55 | 86005
56 | 86005
57 | 86005
58 | 86005
59 | 86005
60 | 86005
61 | 86005
62 | 86005
63 | 86005
64 | 86005
65 | 86005
66 | 86005
67 | 86005
68 | 86005
69 | 86005
70 | 86005
71 | 86005
72 | 86005
73 | 86005
74 | 86005
75 | 86005
76 | 86005
77 | 86005
78 | 86005
79 | 86005
80 | 86005
81 | 86005
82 | 86005
83 | 86005
84 | 86005
85 | 86005
86 | 86005
87 | 86005
88 | 86005
89 | 86005
90 | 86005
91 | 86005
92 | 86005
93 | 86005
94 | 86005
95 | 86005
96 | 86005
97 | 86005
98 | 86240
99 | 86240
100 | 86240
101 | 86240
102 | 86240
103 | 86240
104 | 86240
105 | 86240
106 | 86240
107 | 86240
108 | 86240
109 | 86240
110 | 86240
111 | 86240
112 | 86240
113 | 86240
114 | 86240
115 | 86240
116 | 86240
117 | 86240
118 | 86240
119 | 86240
120 | 86240
121 | 86240
122 | 86240
123 | 86240
124 | 86240
125 | 86240
126 | 86240
127 | 86240
128 | 86240
129 | 86240
130 | 86240
131 | 86240
132 | 86240
133 | 86240
134 | 86240
135 | 86240
136 | 86240
137 | 86240
138 | 86240
139 | 86240
140 | 86240
141 | 86240
142 | 86240
143 | 86240
144 | 86240
145 | 86240
146 | 86240
147 | 86240
148 | 86240
149 | 86240
150 | 86240
151 | 86240
152 | 86240
153 | 86240
154 | 86240
155 | 86240
156 | 86240
157 | 86240
158 | 86240
159 | 86240
160 | 86240
161 | 86240
162 | 86240
163 | 86240
164 | 86240
165 | 86240
166 | 86240
167 | 86240
168 | 86240
169 | 86240
170 | 86240
171 | 86240
172 | 86240
173 | 86240
174 | 86240
175 | 86240
176 | 86240
177 | 86240
178 | 86240
179 | 86240
180 | 86240
181 | 86240
182 | 86240
183 | 86240
184 | 86240
185 | 86240
186 | 86240
187 | 86240
188 | 86240
189 | 86240
190 | 86240
191 | 86240
192 | 86240
193 | 86240
194 | 86240
195 | 86240
196 | 86240
197 | 86240
198 | 86240
199 | 86240
200 | 86240
201 | 86240
202 | 86240
203 | 86240
204 | 86240
205 | 86240
206 | 86240
207 | 86240
208 | 86240
209 | 86240
210 | 86240
211 | 86240
212 | 86240
213 | 86240
214 | 86240
215 | 86240
216 | 86240
217 | 86240
218 | 86240
219 | 86240
220 | 86240
221 | 86240
222 | 86240
223 | 86240
224 | 86240
225 | 86240
226 | 86240
227 | 86240
228 | 86240
229 | 86240
230 | 86240
231 | 86240
232 | 86240
233 | 86240
234 | 86240
235 | 86240
236 | 86240
237 | 86240
238 | 86240
239 | 86240
240 | 86240
241 | 86240
242 | 86240
243 | 86240
244 | 86240
245 | 86240
246 | 86240
247 | 86240
248 | 86240
249 | 86240
250 | 86240
251 | 86240
252 | 86240
253 | 86240
254 | 86240
255 | 86240
256 | 86240
257 | 86240
258 | 86240
259 | 86240
260 | 86240
261 | 86240
262 | 86240
263 | 86240
264 | 86240
265 | 86240
266 | 86240
267 | 86240
268 | 86240
269 | 86240
270 | 86240
271 | 86240
272 | 86240
273 | 86240
274 | 86240
275 | 86240
276 | 86240
277 | 86240
278 | 87220
279 | 87220
280 | 87220
281 | 87220
282 | 87220
283 | 87220
284 | 87220
285 | 87220
286 | 87220
287 | 87220
288 | 87220
289 | 87220
290 | 87220
291 | 87220
292 | 87220
293 | 87220
294 | 87220
295 | 87220
296 | 87220
297 | 87220
298 | 87220
299 | 87220
300 | 87220

## Component_Analysis
Component | Max Weekly Usage | Total Usage | Peak Utilization
Engine | 18 | 143 | 0
Chassis | 18 | 143 | 0
Hydraulics | 33 | 241 | 0
Electronics | 18 | 143 | 0
Tires | 72 | 572 | 0
Battery | 10 | 78 | 0