## Summary
Metric | Value
Planning Start Date | 2025-06-19
Min Early Delivery Days | 7
Total Orders | 50
Valid Assignments | 47
Invalid Assignments (Past) | 0
Too Early Assignments | 0
Orders On Time | 0
Orders Early (Within Window) | 6
Orders Late | 41
On-Time Percentage (%) | 0.0
Total Penalty Cost ($) | 12350.00

## Order_Results
Order Number | Product Id | Customer Priority | Original Promise Date | Optimized Scheduled Date | Delay Days | Is Late | Is Early | Is Too Early | Is Invalid | Order Qty | Revenue
SO0001 | FL001 | High | 2025-09-04 | 2025-09-28 | 23 | TRUE | FALSE | FALSE | FALSE | 1 | 37587.3719
SO0002 | FL002 | Low | 2025-08-21 | 2025-09-14 | 23 | TRUE | FALSE | FALSE | FALSE | 4 | 188691.2963
SO0003 | FL005 | Medium | 2025-07-24 | 2025-08-03 | 9 | TRUE | FALSE | FALSE | FALSE | 3 | 126478.7901
SO0004 | FL001 | High | 2025-07-31 | 2025-09-07 | 37 | TRUE | FALSE | FALSE | FALSE | 5 | 140528.3242
SO0005 | FL001 | High | 2025-08-28 | 2025-08-17 | -11 | FALSE | FALSE | TRUE | FALSE | 5 | 180239.9903
SO0006 | FL005 | Low | 2025-08-07 | 2025-09-21 | 44 | TRUE | FALSE | FALSE | FALSE | 1 | 19983.3521
SO0007 | FL002 | Low | 2025-07-10 | 2025-09-28 | 79 | TRUE | FALSE | FALSE | FALSE | 5 | 82035.1211
SO0008 | FL003 | Medium | 2025-08-07 | 2025-08-03 | -4 | FALSE | TRUE | FALSE | FALSE | 1 | 31073.5483
SO0009 | FL003 | Low | 2025-08-21 | 2025-10-12 | 51 | TRUE | FALSE | FALSE | FALSE | 3 | 78909.72
SO0010 | FL002 | Low | 2025-07-10 | 2025-07-06 | -4 | FALSE | TRUE | FALSE | FALSE | 3 | 119658.2762
SO0011 | FL004 | High | 2025-06-26 | 2025-06-29 | 2 | TRUE | FALSE | FALSE | FALSE | 5 | 170790.5871
SO0012 | FL005 | High | 2025-07-31 | 2025-09-14 | 44 | TRUE | FALSE | FALSE | FALSE | 1 | 49270.0695
SO0013 | FL002 | Low | 2025-07-03 | 2025-10-26 | 114 | TRUE | FALSE | FALSE | FALSE | 2 | 31861.6089
SO0014 | FL005 | Low | 2025-06-26 | 2025-10-05 | 100 | TRUE | FALSE | FALSE | FALSE | 5 | 181849.1241
SO0015 | FL003 | Medium | 2025-08-14 | 2025-08-10 | -4 | FALSE | TRUE | FALSE | FALSE | 1 | 38952.2263
SO0016 | FL003 | High | 2025-08-07 | 2025-08-24 | 16 | TRUE | FALSE | FALSE | FALSE | 2 | 76376.3149
SO0017 | FL005 | Low | 2025-07-24 | 2025-07-27 | 2 | TRUE | FALSE | FALSE | FALSE | 5 | 164594.116
SO0018 | FL003 | Medium | 2025-08-07 | 2025-09-14 | 37 | TRUE | FALSE | FALSE | FALSE | 3 | 141148.4844
SO0019 | FL004 | High | 2025-09-11 | 2025-09-07 | -4 | FALSE | TRUE | FALSE | FALSE | 1 | 16378.2268
SO0020 | FL001 | Low | 2025-07-03 | 2025-07-06 | 2 | TRUE | FALSE | FALSE | FALSE | 5 | 211664.6982
SO0021 | FL001 | High | 2025-08-28 | 2025-08-31 | 2 | TRUE | FALSE | FALSE | FALSE | 4 | 82505.3603
SO0022 | FL001 | Low | 2025-07-17 | 2025-09-21 | 65 | TRUE | FALSE | FALSE | FALSE | 4 | 121209.9214
SO0023 | FL005 | Medium | 2025-07-24 | 2025-08-24 | 30 | TRUE | FALSE | FALSE | FALSE | 4 | 105076.5955
SO0024 | FL005 | Low | 2025-08-21 | 2025-10-12 | 51 | TRUE | FALSE | FALSE | FALSE | 2 | 32133.6849
SO0025 | FL005 | High | 2025-06-26 | 2025-08-31 | 65 | TRUE | FALSE | FALSE | FALSE | 4 | 99112.5601
SO0026 | FL003 | Low | 2025-07-31 | 2025-09-07 | 37 | TRUE | FALSE | FALSE | FALSE | 3 | 52472.5202
SO0027 | FL001 | High | 2025-06-26 | 2025-08-17 | 51 | TRUE | FALSE | FALSE | FALSE | 3 | 102534.0015
SO0028 | FL004 | High | 2025-07-17 | 2025-07-20 | 2 | TRUE | FALSE | FALSE | FALSE | 4 | 77533.3421
SO0029 | FL003 | High | 2025-07-03 | 2025-06-22 | -11 | FALSE | FALSE | TRUE | FALSE | 4 | 99980.6875
SO0030 | FL004 | High | 2025-06-26 | 2025-06-29 | 2 | TRUE | FALSE | FALSE | FALSE | 1 | 42255.8304
SO0031 | FL001 | Low | 2025-08-07 | 2025-08-10 | 2 | TRUE | FALSE | FALSE | FALSE | 1 | 43630.1459
SO0032 | FL001 | High | 2025-08-28 | 2025-08-24 | -4 | FALSE | TRUE | FALSE | FALSE | 3 | 66000.6636
SO0033 | FL002 | High | 2025-06-26 | 2025-09-28 | 93 | TRUE | FALSE | FALSE | FALSE | 1 | 34785.8526
SO0034 | FL001 | Medium | 2025-07-17 | 2025-08-03 | 16 | TRUE | FALSE | FALSE | FALSE | 4 | 98852.2542
SO0035 | FL004 | High | 2025-07-31 | 2025-08-10 | 9 | TRUE | FALSE | FALSE | FALSE | 4 | 181710.4524
SO0036 | FL002 | High | 2025-09-04 | 2025-09-21 | 16 | TRUE | FALSE | FALSE | FALSE | 4 | 102017.9397
SO0037 | FL003 | Low | 2025-07-17 | 2025-08-10 | 23 | TRUE | FALSE | FALSE | FALSE | 4 | 108839.695
SO0038 | FL003 | High | 2025-07-31 | 2025-07-20 | -11 | FALSE | FALSE | TRUE | FALSE | 4 | 70787.3749
SO0039 | FL004 | Low | 2025-08-21 | 2025-10-12 | 51 | TRUE | FALSE | FALSE | FALSE | 2 | 72859.9635
SO0040 | FL002 | Low | 2025-06-26 | 2025-09-07 | 72 | TRUE | FALSE | FALSE | FALSE | 2 | 37245.3191
SO0041 | FL005 | High | 2025-08-14 | 2025-08-17 | 2 | TRUE | FALSE | FALSE | FALSE | 5 | 125840.5168
SO0042 | FL005 | Low | 2025-07-17 | 2025-09-07 | 51 | TRUE | FALSE | FALSE | FALSE | 5 | 247763.1828
SO0043 | FL002 | Medium | 2025-08-14 | 2025-08-17 | 2 | TRUE | FALSE | FALSE | FALSE | 1 | 45562.6458
SO0044 | FL005 | High | 2025-09-11 | 2025-11-02 | 51 | TRUE | FALSE | FALSE | FALSE | 3 | 128043.651
SO0045 | FL002 | Medium | 2025-07-24 | 2025-11-02 | 100 | TRUE | FALSE | FALSE | FALSE | 4 | 76092.9536
SO0046 | FL005 | High | 2025-06-26 | 2025-06-29 | 2 | TRUE | FALSE | FALSE | FALSE | 2 | 77158.0628
SO0047 | FL001 | High | 2025-08-14 | 2025-08-31 | 16 | TRUE | FALSE | FALSE | FALSE | 2 | 61830.6576
SO0048 | FL001 | Low | 2025-06-26 | 2025-07-27 | 30 | TRUE | FALSE | FALSE | FALSE | 4 | 84449.6844
SO0049 | FL002 | High | 2025-07-31 | 2025-08-10 | 9 | TRUE | FALSE | FALSE | FALSE | 3 | 77869.9365
SO0050 | FL004 | Low | 2025-07-17 | 2025-07-13 | -4 | FALSE | TRUE | FALSE | FALSE | 5 | 175172.2915

## Priority_Analysis
Customer Priority | Total Orders | Late Orders | On Time Rate | Avg Delay Days | Total Revenue
High | 23 | 18 | 21.7 | 24.6 | 2101137.77
Low | 19 | 17 | 10.5 | 46.9 | 2055023.72
Medium | 8 | 6 | 25.0 | 32.3 | 663237.50

## Capacity_Utilization
Line Restriction | Max Weekly Usage | Total Usage | Peak Utilization
Welding_Line2 | 10 | 88 | 0
Assembly_B | 8 | 64 | 0
Paint_Line | 16 | 157 | 0
Testing_Station | 16 | 157 | 0
Welding_Line1 | 11 | 69 | 0
Assembly_A | 15 | 93 | 0

## Weekly_Schedule
Order Number | Product Id | Scheduled Date | Operation Id | Line Restriction | Quantity | Customer Priority
SO0001 | FL001 | 2025-09-28 | 0010 | Welding_Line2 | 1 | High
SO0001 | FL001 | 2025-09-28 | 0020 | Assembly_B | 1 | High
SO0001 | FL001 | 2025-09-28 | 0030 | Paint_Line | 1 | High
SO0001 | FL001 | 2025-09-28 | 0040 | Testing_Station | 1 | High
SO0002 | FL002 | 2025-09-14 | 0010 | Welding_Line1 | 4 | Low
SO0002 | FL002 | 2025-09-14 | 0020 | Assembly_B | 4 | Low
SO0002 | FL002 | 2025-09-14 | 0030 | Paint_Line | 4 | Low
SO0002 | FL002 | 2025-09-14 | 0040 | Testing_Station | 4 | Low
SO0003 | FL005 | 2025-08-03 | 0010 | Welding_Line1 | 3 | Medium
SO0003 | FL005 | 2025-08-03 | 0020 | Assembly_A | 3 | Medium
SO0003 | FL005 | 2025-08-03 | 0030 | Paint_Line | 3 | Medium
SO0003 | FL005 | 2025-08-03 | 0040 | Testing_Station | 3 | Medium
SO0004 | FL001 | 2025-09-07 | 0010 | Welding_Line1 | 5 | High
SO0004 | FL001 | 2025-09-07 | 0020 | Assembly_A | 5 | High
SO0004 | FL001 | 2025-09-07 | 0030 | Paint_Line | 5 | High
SO0004 | FL001 | 2025-09-07 | 0040 | Testing_Station | 5 | High
SO0005 | FL001 | 2025-08-17 | 0010 | Welding_Line2 | 5 | High
SO0005 | FL001 | 2025-08-17 | 0020 | Assembly_A | 5 | High
SO0005 | FL001 | 2025-08-17 | 0030 | Paint_Line | 5 | High
SO0005 | FL001 | 2025-08-17 | 0040 | Testing_Station | 5 | High
SO0006 | FL005 | 2025-09-21 | 0010 | Welding_Line2 | 1 | Low
SO0006 | FL005 | 2025-09-21 | 0020 | Assembly_B | 1 | Low
SO0006 | FL005 | 2025-09-21 | 0030 | Paint_Line | 1 | Low
SO0006 | FL005 | 2025-09-21 | 0040 | Testing_Station | 1 | Low
SO0007 | FL002 | 2025-09-28 | 0010 | Welding_Line2 | 5 | Low
SO0007 | FL002 | 2025-09-28 | 0020 | Assembly_A | 5 | Low
SO0007 | FL002 | 2025-09-28 | 0030 | Paint_Line | 5 | Low
SO0007 | FL002 | 2025-09-28 | 0040 | Testing_Station | 5 | Low
SO0008 | FL003 | 2025-08-03 | 0010 | Welding_Line2 | 1 | Medium
SO0008 | FL003 | 2025-08-03 | 0020 | Assembly_B | 1 | Medium
SO0008 | FL003 | 2025-08-03 | 0030 | Paint_Line | 1 | Medium
SO0008 | FL003 | 2025-08-03 | 0040 | Testing_Station | 1 | Medium
SO0009 | FL003 | 2025-10-12 | 0010 | Welding_Line2 | 3 | Low
SO0009 | FL003 | 2025-10-12 | 0020 | Assembly_A | 3 | Low
SO0009 | FL003 | 2025-10-12 | 0030 | Paint_Line | 3 | Low
SO0009 | FL003 | 2025-10-12 | 0040 | Testing_Station | 3 | Low
SO0010 | FL002 | 2025-07-06 | 0010 | Welding_Line2 | 3 | Low
SO0010 | FL002 | 2025-07-06 | 0020 | Assembly_B | 3 | Low
SO0010 | FL002 | 2025-07-06 | 0030 | Paint_Line | 3 | Low
SO0010 | FL002 | 2025-07-06 | 0040 | Testing_Station | 3 | Low
SO0011 | FL004 | 2025-06-29 | 0010 | Welding_Line2 | 5 | High
SO0011 | FL004 | 2025-06-29 | 0020 | Assembly_B | 5 | High
SO0011 | FL004 | 2025-06-29 | 0030 | Paint_Line | 5 | High
SO0011 | FL004 | 2025-06-29 | 0040 | Testing_Station | 5 | High
SO0012 | FL005 | 2025-09-14 | 0010 | Welding_Line1 | 1 | High
SO0012 | FL005 | 2025-09-14 | 0020 | Assembly_B | 1 | High
SO0012 | FL005 | 2025-09-14 | 0030 | Paint_Line | 1 | High
SO0012 | FL005 | 2025-09-14 | 0040 | Testing_Station | 1 | High
SO0013 | FL002 | 2025-10-26 | 0010 | Welding_Line1 | 2 | Low
SO0013 | FL002 | 2025-10-26 | 0020 | Assembly_A | 2 | Low
SO0013 | FL002 | 2025-10-26 | 0030 | Paint_Line | 2 | Low
SO0013 | FL002 | 2025-10-26 | 0040 | Testing_Station | 2 | Low
SO0014 | FL005 | 2025-10-05 | 0010 | Welding_Line2 | 5 | Low
SO0014 | FL005 | 2025-10-05 | 0020 | Assembly_A | 5 | Low
SO0014 | FL005 | 2025-10-05 | 0030 | Paint_Line | 5 | Low
SO0014 | FL005 | 2025-10-05 | 0040 | Testing_Station | 5 | Low
SO0015 | FL003 | 2025-08-10 | 0010 | Welding_Line2 | 1 | Medium
SO0015 | FL003 | 2025-08-10 | 0020 | Assembly_B | 1 | Medium
SO0015 | FL003 | 2025-08-10 | 0030 | Paint_Line | 1 | Medium
SO0015 | FL003 | 2025-08-10 | 0040 | Testing_Station | 1 | Medium
SO0016 | FL003 | 2025-08-24 | 0010 | Welding_Line1 | 2 | High
SO0016 | FL003 | 2025-08-24 | 0020 | Assembly_B | 2 | High
SO0016 | FL003 | 2025-08-24 | 0030 | Paint_Line | 2 | High
SO0016 | FL003 | 2025-08-24 | 0040 | Testing_Station | 2 | High
SO0017 | FL005 | 2025-07-27 | 0010 | Welding_Line2 | 5 | Low
SO0017 | FL005 | 2025-07-27 | 0020 | Assembly_A | 5 | Low
SO0017 | FL005 | 2025-07-27 | 0030 | Paint_Line | 5 | Low
SO0017 | FL005 | 2025-07-27 | 0040 | Testing_Station | 5 | Low
SO0018 | FL003 | 2025-09-14 | 0010 | Welding_Line2 | 3 | Medium
SO0018 | FL003 | 2025-09-14 | 0020 | Assembly_B | 3 | Medium
SO0018 | FL003 | 2025-09-14 | 0030 | Paint_Line | 3 | Medium
SO0018 | FL003 | 2025-09-14 | 0040 | Testing_Station | 3 | Medium
SO0019 | FL004 | 2025-09-07 | 0010 | Welding_Line1 | 1 | High
SO0019 | FL004 | 2025-09-07 | 0020 | Assembly_B | 1 | High
SO0019 | FL004 | 2025-09-07 | 0030 | Paint_Line | 1 | High
SO0019 | FL004 | 2025-09-07 | 0040 | Testing_Station | 1 | High
SO0020 | FL001 | 2025-07-06 | 0010 | Welding_Line2 | 5 | Low
SO0020 | FL001 | 2025-07-06 | 0020 | Assembly_A | 5 | Low
SO0020 | FL001 | 2025-07-06 | 0030 | Paint_Line | 5 | Low
SO0020 | FL001 | 2025-07-06 | 0040 | Testing_Station | 5 | Low
SO0021 | FL001 | 2025-08-31 | 0010 | Welding_Line2 | 4 | High
SO0021 | FL001 | 2025-08-31 | 0020 | Assembly_A | 4 | High
SO0021 | FL001 | 2025-08-31 | 0030 | Paint_Line | 4 | High
SO0021 | FL001 | 2025-08-31 | 0040 | Testing_Station | 4 | High
SO0022 | FL001 | 2025-09-21 | 0010 | Welding_Line2 | 4 | Low
SO0022 | FL001 | 2025-09-21 | 0020 | Assembly_A | 4 | Low
SO0022 | FL001 | 2025-09-21 | 0030 | Paint_Line | 4 | Low
SO0022 | FL001 | 2025-09-21 | 0040 | Testing_Station | 4 | Low
SO0023 | FL005 | 2025-08-24 | 0010 | Welding_Line1 | 4 | Medium
SO0023 | FL005 | 2025-08-24 | 0020 | Assembly_A | 4 | Medium
SO0023 | FL005 | 2025-08-24 | 0030 | Paint_Line | 4 | Medium
SO0023 | FL005 | 2025-08-24 | 0040 | Testing_Station | 4 | Medium
SO0024 | FL005 | 2025-10-12 | 0010 | Welding_Line1 | 2 | Low
SO0024 | FL005 | 2025-10-12 | 0020 | Assembly_A | 2 | Low
SO0024 | FL005 | 2025-10-12 | 0030 | Paint_Line | 2 | Low
SO0024 | FL005 | 2025-10-12 | 0040 | Testing_Station | 2 | Low
SO0025 | FL005 | 2025-08-31 | 0010 | Welding_Line2 | 4 | High
SO0025 | FL005 | 2025-08-31 | 0020 | Assembly_B | 4 | High
SO0025 | FL005 | 2025-08-31 | 0030 | Paint_Line | 4 | High
SO0025 | FL005 | 2025-08-31 | 0040 | Testing_Station | 4 | High
SO0026 | FL003 | 2025-09-07 | 0010 | Welding_Line2 | 3 | Low
SO0026 | FL003 | 2025-09-07 | 0020 | Assembly_A | 3 | Low
SO0026 | FL003 | 2025-09-07 | 0030 | Paint_Line | 3 | Low
SO0026 | FL003 | 2025-09-07 | 0040 | Testing_Station | 3 | Low
SO0027 | FL001 | 2025-08-17 | 0010 | Welding_Line1 | 3 | High
SO0027 | FL001 | 2025-08-17 | 0020 | Assembly_B | 3 | High
SO0027 | FL001 | 2025-08-17 | 0030 | Paint_Line | 3 | High
SO0027 | FL001 | 2025-08-17 | 0040 | Testing_Station | 3 | High
SO0028 | FL004 | 2025-07-20 | 0010 | Welding_Line2 | 4 | High
SO0028 | FL004 | 2025-07-20 | 0020 | Assembly_B | 4 | High
SO0028 | FL004 | 2025-07-20 | 0030 | Paint_Line | 4 | High
SO0028 | FL004 | 2025-07-20 | 0040 | Testing_Station | 4 | High
SO0029 | FL003 | 2025-06-22 | 0010 | Welding_Line2 | 4 | High
SO0029 | FL003 | 2025-06-22 | 0020 | Assembly_B | 4 | High
SO0029 | FL003 | 2025-06-22 | 0030 | Paint_Line | 4 | High
SO0029 | FL003 | 2025-06-22 | 0040 | Testing_Station | 4 | High
SO0030 | FL004 | 2025-06-29 | 0010 | Welding_Line1 | 1 | High
SO0030 | FL004 | 2025-06-29 | 0020 | Assembly_A | 1 | High
SO0030 | FL004 | 2025-06-29 | 0030 | Paint_Line | 1 | High
SO0030 | FL004 | 2025-06-29 | 0040 | Testing_Station | 1 | High
SO0031 | FL001 | 2025-08-10 | 0010 | Welding_Line1 | 1 | Low
SO0031 | FL001 | 2025-08-10 | 0020 | Assembly_B | 1 | Low
SO0031 | FL001 | 2025-08-10 | 0030 | Paint_Line | 1 | Low
SO0031 | FL001 | 2025-08-10 | 0040 | Testing_Station | 1 | Low
SO0032 | FL001 | 2025-08-24 | 0010 | Welding_Line1 | 3 | High
SO0032 | FL001 | 2025-08-24 | 0020 | Assembly_A | 3 | High
SO0032 | FL001 | 2025-08-24 | 0030 | Paint_Line | 3 | High
SO0032 | FL001 | 2025-08-24 | 0040 | Testing_Station | 3 | High
SO0033 | FL002 | 2025-09-28 | 0010 | Welding_Line2 | 1 | High
SO0033 | FL002 | 2025-09-28 | 0020 | Assembly_B | 1 | High
SO0033 | FL002 | 2025-09-28 | 0030 | Paint_Line | 1 | High
SO0033 | FL002 | 2025-09-28 | 0040 | Testing_Station | 1 | High
SO0034 | FL001 | 2025-08-03 | 0010 | Welding_Line2 | 4 | Medium
SO0034 | FL001 | 2025-08-03 | 0020 | Assembly_B | 4 | Medium
SO0034 | FL001 | 2025-08-03 | 0030 | Paint_Line | 4 | Medium
SO0034 | FL001 | 2025-08-03 | 0040 | Testing_Station | 4 | Medium
SO0035 | FL004 | 2025-08-10 | 0010 | Welding_Line2 | 4 | High
SO0035 | FL004 | 2025-08-10 | 0020 | Assembly_A | 4 | High
SO0035 | FL004 | 2025-08-10 | 0030 | Paint_Line | 4 | High
SO0035 | FL004 | 2025-08-10 | 0040 | Testing_Station | 4 | High
SO0036 | FL002 | 2025-09-21 | 0010 | Welding_Line1 | 4 | High
SO0036 | FL002 | 2025-09-21 | 0020 | Assembly_B | 4 | High
SO0036 | FL002 | 2025-09-21 | 0030 | Paint_Line | 4 | High
SO0036 | FL002 | 2025-09-21 | 0040 | Testing_Station | 4 | High
SO0037 | FL003 | 2025-08-10 | 0010 | Welding_Line1 | 4 | Low
SO0037 | FL003 | 2025-08-10 | 0020 | Assembly_B | 4 | Low
SO0037 | FL003 | 2025-08-10 | 0030 | Paint_Line | 4 | Low
SO0037 | FL003 | 2025-08-10 | 0040 | Testing_Station | 4 | Low
SO0038 | FL003 | 2025-07-20 | 0010 | Welding_Line2 | 4 | High
SO0038 | FL003 | 2025-07-20 | 0020 | Assembly_A | 4 | High
SO0038 | FL003 | 2025-07-20 | 0030 | Paint_Line | 4 | High
SO0038 | FL003 | 2025-07-20 | 0040 | Testing_Station | 4 | High
SO0039 | FL004 | 2025-10-12 | 0010 | Welding_Line2 | 2 | Low
SO0039 | FL004 | 2025-10-12 | 0020 | Assembly_A | 2 | Low
SO0039 | FL004 | 2025-10-12 | 0030 | Paint_Line | 2 | Low
SO0039 | FL004 | 2025-10-12 | 0040 | Testing_Station | 2 | Low
SO0040 | FL002 | 2025-09-07 | 0010 | Welding_Line2 | 2 | Low
SO0040 | FL002 | 2025-09-07 | 0020 | Assembly_A | 2 | Low
SO0040 | FL002 | 2025-09-07 | 0030 | Paint_Line | 2 | Low
SO0040 | FL002 | 2025-09-07 | 0040 | Testing_Station | 2 | Low
SO0041 | FL005 | 2025-08-17 | 0010 | Welding_Line1 | 5 | High
SO0041 | FL005 | 2025-08-17 | 0020 | Assembly_A | 5 | High
SO0041 | FL005 | 2025-08-17 | 0030 | Paint_Line | 5 | High
SO0041 | FL005 | 2025-08-17 | 0040 | Testing_Station | 5 | High
SO0042 | FL005 | 2025-09-07 | 0010 | Welding_Line1 | 5 | Low
SO0042 | FL005 | 2025-09-07 | 0020 | Assembly_A | 5 | Low
SO0042 | FL005 | 2025-09-07 | 0030 | Paint_Line | 5 | Low
SO0042 | FL005 | 2025-09-07 | 0040 | Testing_Station | 5 | Low
SO0043 | FL002 | 2025-08-17 | 0010 | Welding_Line1 | 1 | Medium
SO0043 | FL002 | 2025-08-17 | 0020 | Assembly_B | 1 | Medium
SO0043 | FL002 | 2025-08-17 | 0030 | Paint_Line | 1 | Medium
SO0043 | FL002 | 2025-08-17 | 0040 | Testing_Station | 1 | Medium
SO0044 | FL005 | 2025-11-02 | 0010 | Welding_Line1 | 3 | High
SO0044 | FL005 | 2025-11-02 | 0020 | Assembly_A | 3 | High
SO0044 | FL005 | 2025-11-02 | 0030 | Paint_Line | 3 | High
SO0044 | FL005 | 2025-11-02 | 0040 | Testing_Station | 3 | High
SO0045 | FL002 | 2025-11-02 | 0010 | Welding_Line1 | 4 | Medium
SO0045 | FL002 | 2025-11-02 | 0020 | Assembly_A | 4 | Medium
SO0045 | FL002 | 2025-11-02 | 0030 | Paint_Line | 4 | Medium
SO0045 | FL002 | 2025-11-02 | 0040 | Testing_Station | 4 | Medium
SO0046 | FL005 | 2025-06-29 | 0010 | Welding_Line1 | 2 | High
SO0046 | FL005 | 2025-06-29 | 0020 | Assembly_B | 2 | High
SO0046 | FL005 | 2025-06-29 | 0030 | Paint_Line | 2 | High
SO0046 | FL005 | 2025-06-29 | 0040 | Testing_Station | 2 | High
SO0047 | FL001 | 2025-08-31 | 0010 | Welding_Line2 | 2 | High
SO0047 | FL001 | 2025-08-31 | 0020 | Assembly_A | 2 | High
SO0047 | FL001 | 2025-08-31 | 0030 | Paint_Line | 2 | High
SO0047 | FL001 | 2025-08-31 | 0040 | Testing_Station | 2 | High
SO0048 | FL001 | 2025-07-27 | 0010 | Welding_Line1 | 4 | Low
SO0048 | FL001 | 2025-07-27 | 0020 | Assembly_B | 4 | Low
SO0048 | FL001 | 2025-07-27 | 0030 | Paint_Line | 4 | Low
SO0048 | FL001 | 2025-07-27 | 0040 | Testing_Station | 4 | Low
SO0049 | FL002 | 2025-08-10 | 0010 | Welding_Line2 | 3 | High
SO0049 | FL002 | 2025-08-10 | 0020 | Assembly_A | 3 | High
SO0049 | FL002 | 2025-08-10 | 0030 | Paint_Line | 3 | High
SO0049 | FL002 | 2025-08-10 | 0040 | Testing_Station | 3 | High
SO0050 | FL004 | 2025-07-13 | 0010 | Welding_Line1 | 5 | Low
SO0050 | FL004 | 2025-07-13 | 0020 | Assembly_B | 5 | Low
SO0050 | FL004 | 2025-07-13 | 0030 | Paint_Line | 5 | Low
SO0050 | FL004 | 2025-07-13 | 0040 | Testing_Station | 5 | Low

## Fitness_Evolution
Generation | Fitness Score
1 | 69920
2 | 69920
3 | 70520
4 | 74975
5 | 75510
6 | 75845
7 | 75845
8 | 75845
9 | 76245
10 | 76245
11 | 76245
12 | 76245
13 | 76245
14 | 76245
15 | 76245
16 | 76245
17 | 77160
18 | 77605
19 | 77605
20 | 77605
21 | 77605
22 | 77605
23 | 79630
24 | 79630
25 | 79630
26 | 79630
27 | 79630
28 | 79630
29 | 79630
30 | 79630
31 | 79630
32 | 79630
33 | 79630
34 | 79630
35 | 79630
36 | 79630
37 | 79630
38 | 80715
39 | 83025
40 | 83025
41 | 83025
42 | 83025
43 | 83025
44 | 83025
45 | 83025
46 | 83025
47 | 83025
48 | 83025
49 | 83025
50 | 83025
51 | 83025
52 | 84350
53 | 84350
54 | 84350
55 | 84350
56 | 84350
57 | 84350
58 | 84350
59 | 84350
60 | 84350
61 | 84350
62 | 84350
63 | 84350
64 | 84350
65 | 84350
66 | 84350
67 | 84350
68 | 84350
69 | 84350
70 | 84350
71 | 84350
72 | 84350
73 | 84350
74 | 84350
75 | 84350
76 | 84350
77 | 84350
78 | 84350
79 | 84350
80 | 84350
81 | 84350
82 | 84350
83 | 84350
84 | 84350
85 | 84350
86 | 84350
87 | 84350
88 | 84350
89 | 84350
90 | 84350
91 | 84350
92 | 84350
93 | 84350
94 | 84350
95 | 84350
96 | 84350
97 | 84350
98 | 84350
99 | 84350
100 | 84350
101 | 84350
102 | 84350
103 | 84350
104 | 84350
105 | 84350
106 | 84350
107 | 84350
108 | 84350
109 | 84350
110 | 84350
111 | 84350
112 | 84350
113 | 84350
114 | 84350
115 | 84350
116 | 84350
117 | 84350
118 | 84350
119 | 84350
120 | 84350
121 | 84350
122 | 84350
123 | 84350
124 | 84350
125 | 84350
126 | 84350
127 | 84350
128 | 84350
129 | 84350
130 | 84350
131 | 84350
132 | 84350
133 | 84350
134 | 84350
135 | 84350
136 | 84350
137 | 84350
138 | 84350
139 | 84350
140 | 84350
141 | 84350
142 | 84350
143 | 84350
144 | 84350
145 | 84350
146 | 84350
147 | 84350
148 | 84350
149 | 84350
150 | 84350
151 | 84350
152 | 84350
153 | 84350
154 | 84350
155 | 84350
156 | 84350
157 | 84350
158 | 84350
159 | 84350
160 | 84350
161 | 84350
162 | 84350
163 | 84350
164 | 84350
165 | 84350
166 | 84350
167 | 84350
168 | 84350
169 | 84350
170 | 84350
171 | 84350
172 | 84350
173 | 84350
174 | 84350
175 | 84350
176 | 84350
177 | 84350
178 | 84350
179 | 84350
180 | 84350
181 | 84350
182 | 84350
183 | 84350
184 | 84350
185 | 84350
186 | 84350
187 | 84350
188 | 84350
189 | 84350
190 | 84350
191 | 84825
192 | 84825
193 | 84825
194 | 84825
195 | 84825
196 | 84825
197 | 84825
198 | 84825
199 | 84825
200 | 84825
201 | 84825
202 | 84825
203 | 84825
204 | 84825
205 | 84825
206 | 84825
207 | 84825
208 | 84825
209 | 84825
210 | 84825
211 | 84825
212 | 84825
213 | 84825
214 | 84825
215 | 84825
216 | 84825
217 | 84825
218 | 84825
219 | 84825
220 | 84825
221 | 84825
222 | 84825
223 | 84825
224 | 84825
225 | 84825
226 | 84825
227 | 84825
228 | 84825
229 | 84825
230 | 84825
231 | 84825
232 | 84825
233 | 84825
234 | 84825
235 | 84825
236 | 84825
237 | 84825
238 | 84825
239 | 84825
240 | 84825
241 | 84825
242 | 84825
243 | 84825
244 | 84825
245 | 84825
246 | 84825
247 | 84825
248 | 84825
249 | 84825
250 | 84825
251 | 84825
252 | 84825
253 | 84825
254 | 84825
255 | 84825
256 | 84825
257 | 84825
258 | 84825
259 | 84825
260 | 84825
261 | 84825
262 | 84825
263 | 84825
264 | 84825
265 | 84825
266 | 84825
267 | 84825
268 | 84825
269 | 84825
270 | 84825
271 | 85080
272 | 85080
273 | 85080
274 | 85080
275 | 85080
276 | 85080
277 | 85080
278 | 85080
279 | 85080
280 | 85080
281 | 85080
282 | 85080
283 | 85080
284 | 85080
285 | 85080
286 | 85080
287 | 85080
288 | 85080
289 | 85080
290 | 85080
291 | 85080
292 | 85080
293 | 85080
294 | 85080
295 | 85080
296 | 85080
297 | 85080
298 | 85080
299 | 85080
300 | 85080

## Component_Analysis
Component | Max Weekly Usage | Total Usage | Peak Utilization
Engine | 16 | 157 | 0
Chassis | 16 | 157 | 0
Hydraulics | 24 | 248 | 0
Electronics | 16 | 157 | 0
Tires | 64 | 628 | 0
Battery | 13 | 106 | 0