## Summary
Metric | Value
Planning Start Date | 2025-06-19
Min Early Delivery Days | 7
Total Orders | 50
Valid Assignments | 44
Invalid Assignments (Past) | 0
Too Early Assignments | 0
Orders On Time | 0
Orders Early (Within Window) | 6
Orders Late | 38
On-Time Percentage (%) | 0.0
Total Penalty Cost ($) | 9475.00

## Order_Results
Order Number | Product Id | Customer Priority | Original Promise Date | Optimized Scheduled Date | Delay Days | Is Late | Is Early | Is Too Early | Is Invalid | Order Qty | Revenue
SO0001 | FL004 | Medium | 2025-07-31 | 2025-08-17 | 16 | TRUE | FALSE | FALSE | FALSE | 2 | 30952.6776
SO0002 | FL003 | Low | 2025-06-26 | 2025-11-02 | 128 | TRUE | FALSE | FALSE | FALSE | 5 | 238052.0506
SO0003 | FL003 | Low | 2025-07-10 | 2025-06-29 | -11 | FALSE | FALSE | TRUE | FALSE | 4 | 128824.4357
SO0004 | FL005 | Low | 2025-07-17 | 2025-08-03 | 16 | TRUE | FALSE | FALSE | FALSE | 1 | 44265.1872
SO0005 | FL005 | High | 2025-08-28 | 2025-09-14 | 16 | TRUE | FALSE | FALSE | FALSE | 4 | 66149.4958
SO0006 | FL001 | Medium | 2025-08-28 | 2025-08-17 | -11 | FALSE | FALSE | TRUE | FALSE | 4 | 171060.297
SO0007 | FL003 | Medium | 2025-06-26 | 2025-07-20 | 23 | TRUE | FALSE | FALSE | FALSE | 2 | 82646.5905
SO0008 | FL001 | Medium | 2025-07-03 | 2025-08-10 | 37 | TRUE | FALSE | FALSE | FALSE | 4 | 130297.7224
SO0009 | FL002 | High | 2025-07-31 | 2025-07-27 | -4 | FALSE | TRUE | FALSE | FALSE | 5 | 137812.7659
SO0010 | FL002 | Low | 2025-07-31 | 2025-10-19 | 79 | TRUE | FALSE | FALSE | FALSE | 3 | 54836.1534
SO0011 | FL001 | Medium | 2025-07-03 | 2025-06-22 | -11 | FALSE | FALSE | TRUE | FALSE | 3 | 110097.3209
SO0012 | FL002 | Medium | 2025-06-26 | 2025-06-19 | -7 | FALSE | TRUE | FALSE | FALSE | 4 | 144730.4103
SO0013 | FL004 | Low | 2025-06-26 | 2025-06-29 | 2 | TRUE | FALSE | FALSE | FALSE | 1 | 22529.2453
SO0014 | FL001 | Medium | 2025-07-31 | 2025-08-10 | 9 | TRUE | FALSE | FALSE | FALSE | 4 | 140439.2965
SO0015 | FL003 | Low | 2025-07-31 | 2025-10-19 | 79 | TRUE | FALSE | FALSE | FALSE | 1 | 29050.3975
SO0016 | FL001 | High | 2025-08-21 | 2025-09-28 | 37 | TRUE | FALSE | FALSE | FALSE | 3 | 61399.8157
SO0017 | FL002 | Medium | 2025-07-10 | 2025-10-05 | 86 | TRUE | FALSE | FALSE | FALSE | 1 | 21548.2983
SO0018 | FL001 | Low | 2025-08-07 | 2025-10-12 | 65 | TRUE | FALSE | FALSE | FALSE | 4 | 184371.5343
SO0019 | FL002 | Medium | 2025-08-14 | 2025-08-17 | 2 | TRUE | FALSE | FALSE | FALSE | 1 | 39320.8888
SO0020 | FL002 | Low | 2025-07-31 | 2025-10-26 | 86 | TRUE | FALSE | FALSE | FALSE | 3 | 48850.0353
SO0021 | FL003 | Low | 2025-08-14 | 2025-09-21 | 37 | TRUE | FALSE | FALSE | FALSE | 4 | 169074.2899
SO0022 | FL001 | Low | 2025-07-24 | 2025-08-31 | 37 | TRUE | FALSE | FALSE | FALSE | 2 | 44790.5004
SO0023 | FL001 | Medium | 2025-08-14 | 2025-10-19 | 65 | TRUE | FALSE | FALSE | FALSE | 2 | 65304.7165
SO0024 | FL004 | Medium | 2025-07-24 | 2025-08-24 | 30 | TRUE | FALSE | FALSE | FALSE | 4 | 185126.047
SO0025 | FL001 | High | 2025-09-11 | 2025-10-26 | 44 | TRUE | FALSE | FALSE | FALSE | 4 | 152760.3306
SO0026 | FL002 | Low | 2025-07-24 | 2025-07-13 | -11 | FALSE | FALSE | TRUE | FALSE | 3 | 50541.665
SO0027 | FL003 | Low | 2025-07-03 | 2025-10-26 | 114 | TRUE | FALSE | FALSE | FALSE | 3 | 61040.2715
SO0028 | FL005 | Medium | 2025-08-07 | 2025-08-10 | 2 | TRUE | FALSE | FALSE | FALSE | 1 | 35898.8978
SO0029 | FL003 | High | 2025-07-31 | 2025-07-20 | -11 | FALSE | FALSE | TRUE | FALSE | 2 | 97821.1682
SO0030 | FL002 | Low | 2025-07-10 | 2025-07-06 | -4 | FALSE | TRUE | FALSE | FALSE | 1 | 22834.2208
SO0031 | FL003 | High | 2025-07-10 | 2025-07-13 | 2 | TRUE | FALSE | FALSE | FALSE | 2 | 81057.9339
SO0032 | FL001 | High | 2025-07-17 | 2025-07-13 | -4 | FALSE | TRUE | FALSE | FALSE | 2 | 31592.6609
SO0033 | FL005 | High | 2025-08-28 | 2025-09-28 | 30 | TRUE | FALSE | FALSE | FALSE | 3 | 113659.4153
SO0034 | FL002 | Low | 2025-07-17 | 2025-07-27 | 9 | TRUE | FALSE | FALSE | FALSE | 1 | 22408.6367
SO0035 | FL005 | Low | 2025-08-21 | 2025-11-02 | 72 | TRUE | FALSE | FALSE | FALSE | 1 | 26031.9401
SO0036 | FL004 | Medium | 2025-08-21 | 2025-08-24 | 2 | TRUE | FALSE | FALSE | FALSE | 1 | 16462.9821
SO0037 | FL002 | Medium | 2025-09-04 | 2025-08-31 | -4 | FALSE | TRUE | FALSE | FALSE | 2 | 41942.0851
SO0038 | FL001 | High | 2025-07-24 | 2025-08-03 | 9 | TRUE | FALSE | FALSE | FALSE | 1 | 42935.1082
SO0039 | FL002 | Medium | 2025-08-21 | 2025-09-21 | 30 | TRUE | FALSE | FALSE | FALSE | 2 | 34464.8885
SO0040 | FL001 | Low | 2025-07-03 | 2025-07-20 | 16 | TRUE | FALSE | FALSE | FALSE | 1 | 47026.0123
SO0041 | FL001 | High | 2025-07-24 | 2025-07-20 | -4 | FALSE | TRUE | FALSE | FALSE | 1 | 36666.9086
SO0042 | FL002 | Medium | 2025-07-10 | 2025-08-03 | 23 | TRUE | FALSE | FALSE | FALSE | 2 | 85976.2027
SO0043 | FL004 | Medium | 2025-08-28 | 2025-09-07 | 9 | TRUE | FALSE | FALSE | FALSE | 2 | 65023.3744
SO0044 | FL001 | Low | 2025-07-17 | 2025-08-31 | 44 | TRUE | FALSE | FALSE | FALSE | 3 | 107423.6108
SO0045 | FL002 | Low | 2025-08-28 | 2025-10-19 | 51 | TRUE | FALSE | FALSE | FALSE | 4 | 193212.9718
SO0046 | FL002 | Medium | 2025-07-10 | 2025-07-20 | 9 | TRUE | FALSE | FALSE | FALSE | 1 | 47328.4969
SO0047 | FL005 | Low | 2025-08-14 | 2025-08-31 | 16 | TRUE | FALSE | FALSE | FALSE | 5 | 239260.1338
SO0048 | FL001 | High | 2025-07-17 | 2025-08-03 | 16 | TRUE | FALSE | FALSE | FALSE | 2 | 51138.2526
SO0049 | FL002 | Low | 2025-07-24 | 2025-07-13 | -11 | FALSE | FALSE | TRUE | FALSE | 5 | 179441.2713
SO0050 | FL003 | High | 2025-08-07 | 2025-09-07 | 30 | TRUE | FALSE | FALSE | FALSE | 3 | 102329.0295

## Priority_Analysis
Customer Priority | Total Orders | Late Orders | On Time Rate | Avg Delay Days | Total Revenue
Medium | 18 | 14 | 22.2 | 24.5 | 1448621.19
Low | 20 | 16 | 20.0 | 53.2 | 1913864.56
High | 12 | 8 | 33.3 | 23.0 | 975322.89

## Capacity_Utilization
Line Restriction | Max Weekly Usage | Total Usage | Peak Utilization
Welding_Line2 | 10 | 71 | 0
Assembly_A | 10 | 71 | 0
Paint_Line | 12 | 129 | 0
Testing_Station | 12 | 129 | 0
Welding_Line1 | 7 | 58 | 0
Assembly_B | 10 | 58 | 0

## Weekly_Schedule
Order Number | Product Id | Scheduled Date | Operation Id | Line Restriction | Quantity | Customer Priority
SO0001 | FL004 | 2025-08-17 | 0010 | Welding_Line2 | 2 | Medium
SO0001 | FL004 | 2025-08-17 | 0020 | Assembly_A | 2 | Medium
SO0001 | FL004 | 2025-08-17 | 0030 | Paint_Line | 2 | Medium
SO0001 | FL004 | 2025-08-17 | 0040 | Testing_Station | 2 | Medium
SO0002 | FL003 | 2025-11-02 | 0010 | Welding_Line1 | 5 | Low
SO0002 | FL003 | 2025-11-02 | 0020 | Assembly_A | 5 | Low
SO0002 | FL003 | 2025-11-02 | 0030 | Paint_Line | 5 | Low
SO0002 | FL003 | 2025-11-02 | 0040 | Testing_Station | 5 | Low
SO0003 | FL003 | 2025-06-29 | 0010 | Welding_Line1 | 4 | Low
SO0003 | FL003 | 2025-06-29 | 0020 | Assembly_B | 4 | Low
SO0003 | FL003 | 2025-06-29 | 0030 | Paint_Line | 4 | Low
SO0003 | FL003 | 2025-06-29 | 0040 | Testing_Station | 4 | Low
SO0004 | FL005 | 2025-08-03 | 0010 | Welding_Line2 | 1 | Low
SO0004 | FL005 | 2025-08-03 | 0020 | Assembly_B | 1 | Low
SO0004 | FL005 | 2025-08-03 | 0030 | Paint_Line | 1 | Low
SO0004 | FL005 | 2025-08-03 | 0040 | Testing_Station | 1 | Low
SO0005 | FL005 | 2025-09-14 | 0010 | Welding_Line1 | 4 | High
SO0005 | FL005 | 2025-09-14 | 0020 | Assembly_A | 4 | High
SO0005 | FL005 | 2025-09-14 | 0030 | Paint_Line | 4 | High
SO0005 | FL005 | 2025-09-14 | 0040 | Testing_Station | 4 | High
SO0006 | FL001 | 2025-08-17 | 0010 | Welding_Line2 | 4 | Medium
SO0006 | FL001 | 2025-08-17 | 0020 | Assembly_A | 4 | Medium
SO0006 | FL001 | 2025-08-17 | 0030 | Paint_Line | 4 | Medium
SO0006 | FL001 | 2025-08-17 | 0040 | Testing_Station | 4 | Medium
SO0007 | FL003 | 2025-07-20 | 0010 | Welding_Line2 | 2 | Medium
SO0007 | FL003 | 2025-07-20 | 0020 | Assembly_B | 2 | Medium
SO0007 | FL003 | 2025-07-20 | 0030 | Paint_Line | 2 | Medium
SO0007 | FL003 | 2025-07-20 | 0040 | Testing_Station | 2 | Medium
SO0008 | FL001 | 2025-08-10 | 0010 | Welding_Line1 | 4 | Medium
SO0008 | FL001 | 2025-08-10 | 0020 | Assembly_A | 4 | Medium
SO0008 | FL001 | 2025-08-10 | 0030 | Paint_Line | 4 | Medium
SO0008 | FL001 | 2025-08-10 | 0040 | Testing_Station | 4 | Medium
SO0009 | FL002 | 2025-07-27 | 0010 | Welding_Line2 | 5 | High
SO0009 | FL002 | 2025-07-27 | 0020 | Assembly_A | 5 | High
SO0009 | FL002 | 2025-07-27 | 0030 | Paint_Line | 5 | High
SO0009 | FL002 | 2025-07-27 | 0040 | Testing_Station | 5 | High
SO0010 | FL002 | 2025-10-19 | 0010 | Welding_Line1 | 3 | Low
SO0010 | FL002 | 2025-10-19 | 0020 | Assembly_B | 3 | Low
SO0010 | FL002 | 2025-10-19 | 0030 | Paint_Line | 3 | Low
SO0010 | FL002 | 2025-10-19 | 0040 | Testing_Station | 3 | Low
SO0011 | FL001 | 2025-06-22 | 0010 | Welding_Line2 | 3 | Medium
SO0011 | FL001 | 2025-06-22 | 0020 | Assembly_B | 3 | Medium
SO0011 | FL001 | 2025-06-22 | 0030 | Paint_Line | 3 | Medium
SO0011 | FL001 | 2025-06-22 | 0040 | Testing_Station | 3 | Medium
SO0012 | FL002 | 2025-06-19 | 0010 | Welding_Line2 | 4 | Medium
SO0012 | FL002 | 2025-06-19 | 0020 | Assembly_A | 4 | Medium
SO0012 | FL002 | 2025-06-19 | 0030 | Paint_Line | 4 | Medium
SO0012 | FL002 | 2025-06-19 | 0040 | Testing_Station | 4 | Medium
SO0013 | FL004 | 2025-06-29 | 0010 | Welding_Line1 | 1 | Low
SO0013 | FL004 | 2025-06-29 | 0020 | Assembly_A | 1 | Low
SO0013 | FL004 | 2025-06-29 | 0030 | Paint_Line | 1 | Low
SO0013 | FL004 | 2025-06-29 | 0040 | Testing_Station | 1 | Low
SO0014 | FL001 | 2025-08-10 | 0010 | Welding_Line2 | 4 | Medium
SO0014 | FL001 | 2025-08-10 | 0020 | Assembly_B | 4 | Medium
SO0014 | FL001 | 2025-08-10 | 0030 | Paint_Line | 4 | Medium
SO0014 | FL001 | 2025-08-10 | 0040 | Testing_Station | 4 | Medium
SO0015 | FL003 | 2025-10-19 | 0010 | Welding_Line2 | 1 | Low
SO0015 | FL003 | 2025-10-19 | 0020 | Assembly_A | 1 | Low
SO0015 | FL003 | 2025-10-19 | 0030 | Paint_Line | 1 | Low
SO0015 | FL003 | 2025-10-19 | 0040 | Testing_Station | 1 | Low
SO0016 | FL001 | 2025-09-28 | 0010 | Welding_Line2 | 3 | High
SO0016 | FL001 | 2025-09-28 | 0020 | Assembly_B | 3 | High
SO0016 | FL001 | 2025-09-28 | 0030 | Paint_Line | 3 | High
SO0016 | FL001 | 2025-09-28 | 0040 | Testing_Station | 3 | High
SO0017 | FL002 | 2025-10-05 | 0010 | Welding_Line1 | 1 | Medium
SO0017 | FL002 | 2025-10-05 | 0020 | Assembly_A | 1 | Medium
SO0017 | FL002 | 2025-10-05 | 0030 | Paint_Line | 1 | Medium
SO0017 | FL002 | 2025-10-05 | 0040 | Testing_Station | 1 | Medium
SO0018 | FL001 | 2025-10-12 | 0010 | Welding_Line1 | 4 | Low
SO0018 | FL001 | 2025-10-12 | 0020 | Assembly_B | 4 | Low
SO0018 | FL001 | 2025-10-12 | 0030 | Paint_Line | 4 | Low
SO0018 | FL001 | 2025-10-12 | 0040 | Testing_Station | 4 | Low
SO0019 | FL002 | 2025-08-17 | 0010 | Welding_Line2 | 1 | Medium
SO0019 | FL002 | 2025-08-17 | 0020 | Assembly_A | 1 | Medium
SO0019 | FL002 | 2025-08-17 | 0030 | Paint_Line | 1 | Medium
SO0019 | FL002 | 2025-08-17 | 0040 | Testing_Station | 1 | Medium
SO0020 | FL002 | 2025-10-26 | 0010 | Welding_Line2 | 3 | Low
SO0020 | FL002 | 2025-10-26 | 0020 | Assembly_B | 3 | Low
SO0020 | FL002 | 2025-10-26 | 0030 | Paint_Line | 3 | Low
SO0020 | FL002 | 2025-10-26 | 0040 | Testing_Station | 3 | Low
SO0021 | FL003 | 2025-09-21 | 0010 | Welding_Line1 | 4 | Low
SO0021 | FL003 | 2025-09-21 | 0020 | Assembly_B | 4 | Low
SO0021 | FL003 | 2025-09-21 | 0030 | Paint_Line | 4 | Low
SO0021 | FL003 | 2025-09-21 | 0040 | Testing_Station | 4 | Low
SO0022 | FL001 | 2025-08-31 | 0010 | Welding_Line1 | 2 | Low
SO0022 | FL001 | 2025-08-31 | 0020 | Assembly_A | 2 | Low
SO0022 | FL001 | 2025-08-31 | 0030 | Paint_Line | 2 | Low
SO0022 | FL001 | 2025-08-31 | 0040 | Testing_Station | 2 | Low
SO0023 | FL001 | 2025-10-19 | 0010 | Welding_Line2 | 2 | Medium
SO0023 | FL001 | 2025-10-19 | 0020 | Assembly_A | 2 | Medium
SO0023 | FL001 | 2025-10-19 | 0030 | Paint_Line | 2 | Medium
SO0023 | FL001 | 2025-10-19 | 0040 | Testing_Station | 2 | Medium
SO0024 | FL004 | 2025-08-24 | 0010 | Welding_Line1 | 4 | Medium
SO0024 | FL004 | 2025-08-24 | 0020 | Assembly_A | 4 | Medium
SO0024 | FL004 | 2025-08-24 | 0030 | Paint_Line | 4 | Medium
SO0024 | FL004 | 2025-08-24 | 0040 | Testing_Station | 4 | Medium
SO0025 | FL001 | 2025-10-26 | 0010 | Welding_Line2 | 4 | High
SO0025 | FL001 | 2025-10-26 | 0020 | Assembly_B | 4 | High
SO0025 | FL001 | 2025-10-26 | 0030 | Paint_Line | 4 | High
SO0025 | FL001 | 2025-10-26 | 0040 | Testing_Station | 4 | High
SO0026 | FL002 | 2025-07-13 | 0010 | Welding_Line2 | 3 | Low
SO0026 | FL002 | 2025-07-13 | 0020 | Assembly_B | 3 | Low
SO0026 | FL002 | 2025-07-13 | 0030 | Paint_Line | 3 | Low
SO0026 | FL002 | 2025-07-13 | 0040 | Testing_Station | 3 | Low
SO0027 | FL003 | 2025-10-26 | 0010 | Welding_Line2 | 3 | Low
SO0027 | FL003 | 2025-10-26 | 0020 | Assembly_A | 3 | Low
SO0027 | FL003 | 2025-10-26 | 0030 | Paint_Line | 3 | Low
SO0027 | FL003 | 2025-10-26 | 0040 | Testing_Station | 3 | Low
SO0028 | FL005 | 2025-08-10 | 0010 | Welding_Line1 | 1 | Medium
SO0028 | FL005 | 2025-08-10 | 0020 | Assembly_B | 1 | Medium
SO0028 | FL005 | 2025-08-10 | 0030 | Paint_Line | 1 | Medium
SO0028 | FL005 | 2025-08-10 | 0040 | Testing_Station | 1 | Medium
SO0029 | FL003 | 2025-07-20 | 0010 | Welding_Line2 | 2 | High
SO0029 | FL003 | 2025-07-20 | 0020 | Assembly_B | 2 | High
SO0029 | FL003 | 2025-07-20 | 0030 | Paint_Line | 2 | High
SO0029 | FL003 | 2025-07-20 | 0040 | Testing_Station | 2 | High
SO0030 | FL002 | 2025-07-06 | 0010 | Welding_Line1 | 1 | Low
SO0030 | FL002 | 2025-07-06 | 0020 | Assembly_A | 1 | Low
SO0030 | FL002 | 2025-07-06 | 0030 | Paint_Line | 1 | Low
SO0030 | FL002 | 2025-07-06 | 0040 | Testing_Station | 1 | Low
SO0031 | FL003 | 2025-07-13 | 0010 | Welding_Line1 | 2 | High
SO0031 | FL003 | 2025-07-13 | 0020 | Assembly_B | 2 | High
SO0031 | FL003 | 2025-07-13 | 0030 | Paint_Line | 2 | High
SO0031 | FL003 | 2025-07-13 | 0040 | Testing_Station | 2 | High
SO0032 | FL001 | 2025-07-13 | 0010 | Welding_Line1 | 2 | High
SO0032 | FL001 | 2025-07-13 | 0020 | Assembly_A | 2 | High
SO0032 | FL001 | 2025-07-13 | 0030 | Paint_Line | 2 | High
SO0032 | FL001 | 2025-07-13 | 0040 | Testing_Station | 2 | High
SO0033 | FL005 | 2025-09-28 | 0010 | Welding_Line2 | 3 | High
SO0033 | FL005 | 2025-09-28 | 0020 | Assembly_B | 3 | High
SO0033 | FL005 | 2025-09-28 | 0030 | Paint_Line | 3 | High
SO0033 | FL005 | 2025-09-28 | 0040 | Testing_Station | 3 | High
SO0034 | FL002 | 2025-07-27 | 0010 | Welding_Line2 | 1 | Low
SO0034 | FL002 | 2025-07-27 | 0020 | Assembly_B | 1 | Low
SO0034 | FL002 | 2025-07-27 | 0030 | Paint_Line | 1 | Low
SO0034 | FL002 | 2025-07-27 | 0040 | Testing_Station | 1 | Low
SO0035 | FL005 | 2025-11-02 | 0010 | Welding_Line2 | 1 | Low
SO0035 | FL005 | 2025-11-02 | 0020 | Assembly_B | 1 | Low
SO0035 | FL005 | 2025-11-02 | 0030 | Paint_Line | 1 | Low
SO0035 | FL005 | 2025-11-02 | 0040 | Testing_Station | 1 | Low
SO0036 | FL004 | 2025-08-24 | 0010 | Welding_Line2 | 1 | Medium
SO0036 | FL004 | 2025-08-24 | 0020 | Assembly_A | 1 | Medium
SO0036 | FL004 | 2025-08-24 | 0030 | Paint_Line | 1 | Medium
SO0036 | FL004 | 2025-08-24 | 0040 | Testing_Station | 1 | Medium
SO0037 | FL002 | 2025-08-31 | 0010 | Welding_Line2 | 2 | Medium
SO0037 | FL002 | 2025-08-31 | 0020 | Assembly_B | 2 | Medium
SO0037 | FL002 | 2025-08-31 | 0030 | Paint_Line | 2 | Medium
SO0037 | FL002 | 2025-08-31 | 0040 | Testing_Station | 2 | Medium
SO0038 | FL001 | 2025-08-03 | 0010 | Welding_Line2 | 1 | High
SO0038 | FL001 | 2025-08-03 | 0020 | Assembly_A | 1 | High
SO0038 | FL001 | 2025-08-03 | 0030 | Paint_Line | 1 | High
SO0038 | FL001 | 2025-08-03 | 0040 | Testing_Station | 1 | High
SO0039 | FL002 | 2025-09-21 | 0010 | Welding_Line2 | 2 | Medium
SO0039 | FL002 | 2025-09-21 | 0020 | Assembly_A | 2 | Medium
SO0039 | FL002 | 2025-09-21 | 0030 | Paint_Line | 2 | Medium
SO0039 | FL002 | 2025-09-21 | 0040 | Testing_Station | 2 | Medium
SO0040 | FL001 | 2025-07-20 | 0010 | Welding_Line2 | 1 | Low
SO0040 | FL001 | 2025-07-20 | 0020 | Assembly_A | 1 | Low
SO0040 | FL001 | 2025-07-20 | 0030 | Paint_Line | 1 | Low
SO0040 | FL001 | 2025-07-20 | 0040 | Testing_Station | 1 | Low
SO0041 | FL001 | 2025-07-20 | 0010 | Welding_Line1 | 1 | High
SO0041 | FL001 | 2025-07-20 | 0020 | Assembly_B | 1 | High
SO0041 | FL001 | 2025-07-20 | 0030 | Paint_Line | 1 | High
SO0041 | FL001 | 2025-07-20 | 0040 | Testing_Station | 1 | High
SO0042 | FL002 | 2025-08-03 | 0010 | Welding_Line1 | 2 | Medium
SO0042 | FL002 | 2025-08-03 | 0020 | Assembly_A | 2 | Medium
SO0042 | FL002 | 2025-08-03 | 0030 | Paint_Line | 2 | Medium
SO0042 | FL002 | 2025-08-03 | 0040 | Testing_Station | 2 | Medium
SO0043 | FL004 | 2025-09-07 | 0010 | Welding_Line2 | 2 | Medium
SO0043 | FL004 | 2025-09-07 | 0020 | Assembly_A | 2 | Medium
SO0043 | FL004 | 2025-09-07 | 0030 | Paint_Line | 2 | Medium
SO0043 | FL004 | 2025-09-07 | 0040 | Testing_Station | 2 | Medium
SO0044 | FL001 | 2025-08-31 | 0010 | Welding_Line1 | 3 | Low
SO0044 | FL001 | 2025-08-31 | 0020 | Assembly_A | 3 | Low
SO0044 | FL001 | 2025-08-31 | 0030 | Paint_Line | 3 | Low
SO0044 | FL001 | 2025-08-31 | 0040 | Testing_Station | 3 | Low
SO0045 | FL002 | 2025-10-19 | 0010 | Welding_Line1 | 4 | Low
SO0045 | FL002 | 2025-10-19 | 0020 | Assembly_A | 4 | Low
SO0045 | FL002 | 2025-10-19 | 0030 | Paint_Line | 4 | Low
SO0045 | FL002 | 2025-10-19 | 0040 | Testing_Station | 4 | Low
SO0046 | FL002 | 2025-07-20 | 0010 | Welding_Line1 | 1 | Medium
SO0046 | FL002 | 2025-07-20 | 0020 | Assembly_A | 1 | Medium
SO0046 | FL002 | 2025-07-20 | 0030 | Paint_Line | 1 | Medium
SO0046 | FL002 | 2025-07-20 | 0040 | Testing_Station | 1 | Medium
SO0047 | FL005 | 2025-08-31 | 0010 | Welding_Line2 | 5 | Low
SO0047 | FL005 | 2025-08-31 | 0020 | Assembly_A | 5 | Low
SO0047 | FL005 | 2025-08-31 | 0030 | Paint_Line | 5 | Low
SO0047 | FL005 | 2025-08-31 | 0040 | Testing_Station | 5 | Low
SO0048 | FL001 | 2025-08-03 | 0010 | Welding_Line1 | 2 | High
SO0048 | FL001 | 2025-08-03 | 0020 | Assembly_B | 2 | High
SO0048 | FL001 | 2025-08-03 | 0030 | Paint_Line | 2 | High
SO0048 | FL001 | 2025-08-03 | 0040 | Testing_Station | 2 | High
SO0049 | FL002 | 2025-07-13 | 0010 | Welding_Line2 | 5 | Low
SO0049 | FL002 | 2025-07-13 | 0020 | Assembly_B | 5 | Low
SO0049 | FL002 | 2025-07-13 | 0030 | Paint_Line | 5 | Low
SO0049 | FL002 | 2025-07-13 | 0040 | Testing_Station | 5 | Low
SO0050 | FL003 | 2025-09-07 | 0010 | Welding_Line1 | 3 | High
SO0050 | FL003 | 2025-09-07 | 0020 | Assembly_A | 3 | High
SO0050 | FL003 | 2025-09-07 | 0030 | Paint_Line | 3 | High
SO0050 | FL003 | 2025-09-07 | 0040 | Testing_Station | 3 | High

## Fitness_Evolution
Generation | Fitness Score
1 | 75360
2 | 80615
3 | 80615
4 | 83210
5 | 85670
6 | 85740
7 | 85745
8 | 86375
9 | 87095
10 | 87105
11 | 87815
12 | 87815
13 | 87815
14 | 87815
15 | 87815
16 | 87815
17 | 87815
18 | 87815
19 | 87815
20 | 87815
21 | 87815
22 | 87815
23 | 87815
24 | 87815
25 | 87815
26 | 87815
27 | 87815
28 | 88290
29 | 88290
30 | 88290
31 | 88290
32 | 88290
33 | 88290
34 | 88290
35 | 88290
36 | 88775
37 | 88775
38 | 88775
39 | 88775
40 | 88775
41 | 88775
42 | 88775
43 | 88775
44 | 88775
45 | 88775
46 | 88775
47 | 88775
48 | 88775
49 | 88775
50 | 88775
51 | 88775
52 | 89425
53 | 89425
54 | 89425
55 | 89425
56 | 89425
57 | 89425
58 | 89425
59 | 89425
60 | 90270
61 | 90270
62 | 90270
63 | 90270
64 | 90270
65 | 90270
66 | 90270
67 | 90270
68 | 90270
69 | 90270
70 | 90270
71 | 90270
72 | 90270
73 | 90270
74 | 90270
75 | 90270
76 | 90270
77 | 90270
78 | 90270
79 | 90270
80 | 90270
81 | 90270
82 | 90270
83 | 90270
84 | 90270
85 | 90270
86 | 90270
87 | 90270
88 | 90270
89 | 90270
90 | 90270
91 | 90270
92 | 90270
93 | 90270
94 | 90270
95 | 90270
96 | 90270
97 | 90270
98 | 90270
99 | 90270
100 | 90270
101 | 90270
102 | 90270
103 | 90270
104 | 90270
105 | 90270
106 | 90270
107 | 90270
108 | 90270
109 | 91275
110 | 91275
111 | 91275
112 | 91275
113 | 91275
114 | 91275
115 | 91275
116 | 91275
117 | 91275
118 | 91275
119 | 91275
120 | 91275
121 | 91275
122 | 91275
123 | 91275
124 | 91275
125 | 91275
126 | 91275
127 | 91275
128 | 91275
129 | 91275
130 | 91275
131 | 91275
132 | 91275
133 | 91275
134 | 91275
135 | 91275
136 | 91275
137 | 91275
138 | 91275
139 | 91275
140 | 91275
141 | 91275
142 | 91275
143 | 91275
144 | 91275
145 | 91275
146 | 91275
147 | 91275
148 | 91275
149 | 91275
150 | 91275
151 | 91275
152 | 91275
153 | 91275
154 | 91275
155 | 91275
156 | 91275
157 | 91275
158 | 91275
159 | 91275
160 | 91275
161 | 91275
162 | 91275
163 | 91275
164 | 91275
165 | 91275
166 | 91275
167 | 91275
168 | 91275
169 | 91275
170 | 91275
171 | 91275
172 | 91275
173 | 91275
174 | 91275
175 | 91275
176 | 91275
177 | 91275
178 | 91275
179 | 91275
180 | 91275
181 | 91275
182 | 91275
183 | 91275
184 | 91275
185 | 91275
186 | 91275
187 | 91275
188 | 91275
189 | 91275
190 | 91275
191 | 91275
192 | 91275
193 | 91275
194 | 91275
195 | 91275
196 | 91275
197 | 91275
198 | 91275
199 | 91275
200 | 91275
201 | 91275
202 | 91275
203 | 91275
204 | 91275
205 | 91275
206 | 91275
207 | 91275
208 | 91275
209 | 91275
210 | 91275
211 | 91275
212 | 91275
213 | 91275
214 | 91275
215 | 91275
216 | 91275
217 | 91275
218 | 91275
219 | 91275
220 | 91275
221 | 91275
222 | 91275
223 | 91275
224 | 91275
225 | 91275
226 | 91275
227 | 91275
228 | 91275
229 | 91275
230 | 91275
231 | 91275
232 | 91275
233 | 91275
234 | 91275
235 | 91275
236 | 91275
237 | 91275
238 | 91275
239 | 91275
240 | 91275
241 | 91275
242 | 91275
243 | 91275
244 | 91275
245 | 91275
246 | 91275
247 | 91275
248 | 91275
249 | 91275
250 | 91275
251 | 91275
252 | 91275
253 | 91275
254 | 91275
255 | 91275
256 | 91275
257 | 91275
258 | 91275
259 | 91275
260 | 91275
261 | 91275
262 | 91275
263 | 91275
264 | 91275
265 | 91275
266 | 91275
267 | 91275
268 | 91275
269 | 91275
270 | 91275
271 | 91275
272 | 91275
273 | 91275
274 | 91275
275 | 91275
276 | 91275
277 | 91275
278 | 91275
279 | 91275
280 | 91275
281 | 91275
282 | 91275
283 | 91275
284 | 91275
285 | 91275
286 | 91275
287 | 91275
288 | 91275
289 | 91275
290 | 91275
291 | 91275
292 | 91275
293 | 91275
294 | 91275
295 | 91275
296 | 91275
297 | 91275
298 | 91275
299 | 91275
300 | 91275

## Component_Analysis
Component | Max Weekly Usage | Total Usage | Peak Utilization
Engine | 12 | 129 | 0
Chassis | 12 | 129 | 0
Hydraulics | 20 | 192 | 0
Electronics | 12 | 129 | 0
Tires | 48 | 516 | 0
Battery | 10 | 81 | 0